## Notes
1. The remaining scope based on Estimate in Days of not closed Epics is pessimistic because some Stories/Spikes/Tech Debts/DevOps that are already closed are not taken into account.
2. The remaining scope based on Story Points of not closed Stories/Spikes/Tech Debts/DevOps is optimistic because not all Epics are decomposed.
3. The remaining scope based on Epic Remaining Estimate (a script field) of not closed Epics is more realistic. The Epic Remaining Estimate field is calculated as follows:
* 0 for closed Epics.
* The Story Points of closed Stories/Spikes/Tech Debts/DevOps are deducted from the Epic Total Estimate (another script field), which is calculated as:
* For Epics before Ready status - Max of Estimate in Days of the Epic and Story Points of all not cancelled Stories/Spikes/Tech Debts.
* For Epics in Ready status or further, except Done - Story Points of all not cancelled Stories/Spikes/Tech Debts. Here we assume that the Epic is decomposed and the cost of Stories/Spikes/Tech Debts/DevOps has precedence over the cost of the Epic itself.
4. Stories/Spikes/Tech Debt/DevOps are Decomposed if they are in Ready status or further.
5. Epic Decomposition Progress is calculated as the ratio of Story Estimate to Total Estimate.
6. Story Decomposition Progress is calculated as the ratio of Decomposed to Total Estimate.

## Bugs
Not Closed Bugs
Release | (All)
Type | Bug
Team | Bug Count | Sum of Story Points
Grand Total

## Features (Stories)
To | (Multiple Items)
Not DevOps | Yes
Releases | (All)
Row Labels | Total Estimate | Decomposed (Ready, In Dev, Closed) | Remaining Estimate (Not Closed/Not Decomposed) | Decomposition Progress | Development Progress
COM Mapping for Most-Used Application Types | 5 |  |  | 0% | 100%
(blank) | 5 |  |  | 0% | 100%
Epic: Decomposition | 5 |  |  | 0% | 100%
Export COM to Blue Prism | 10 |  |  | 0% | 100%
NEEDS FOR FILTERING IN PIVOT TABLES | 10 |  |  | 0% | 100%
Epic: Review | 10 |  |  | 0% | 100%
Grand Total | 15 |  |  | 0% | 100%

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Release | Priority | Customer | Team Grouped | Epic Team Grouped | Epic Fully Decomposed | Different Story Points | Not DevOps | Backlog Health | Active in Release # | Quality Score | Story Decomposed | Story Decomposed SP | Story Remaining SP | Releases | Release Component | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-6-6-planning-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getSprints(issue)} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${issue.fixVersions.name} | ${issue.priority.name} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | $[IF(K2="DevOps","", "Yes")] | ${bpHelper.isInBacklogHealth(issue)} |  | ${fieldHelper.getFieldValueByName(issue, "Quality Score")} | ${bpHelper.isStoryDecopmosed(issue)} | $[IF(AP2="Yes", N2, IF(AP2="No",0,""))] | $[IF(E2="Story: Done",0,IF(OR(B2="Story",B2="Spike"), N2, ""))] | ${bpHelper.getReleases(issue)} | ${bpHelper.getReleaseComponent(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | RD | Epic: New | [16 empty] | RD | [8 empty] | Blueprint (5.2) |  |  | RD | RD |  |  | Yes | Yes |  | POC |  |  |  |  | Add Username to Pendo Visitor Name
key | Story |  | RD | Epic: Decomposition | [8 empty] | 5 | [7 empty] | RD | [8 empty] | Blueprint (5.2) |  |  | RD | RD |  |  | Yes | Yes |  | PROD | Yes |  |  |  | COM Mapping for Most-Used Application Types
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | RD | Epic: Review | [8 empty] | 10 | [7 empty] | RD | [8 empty] | AgileTM (13.2) |  |  | RD | RD |  |  | Yes | Yes |  |  | No |  |  |  | Export COM to Blue Prism
key | Tech Debt |  | RD | Epic: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | AgileTM (13.2) |  |  | RD | RD |  |  | Yes | Yes | [6 empty] | Import from Word MVP
key | Bug |  | RD | Epic: In Development | [16 empty] | RD | [11 empty] | RD | RD |  |  | Yes | Yes | [6 empty] | Import UiPath into COM
key |  |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [11 empty] | Unassigned | Unassigned |  |  | Yes | Yes | [6 empty] | Convert Custom Properties to Standard
key |  |  | RD | Epic: Cancelled | [16 empty] | RD | [11 empty] | RD | RD |  |  | Yes | [7 empty] | Pre-Loaded Instance Configuration
key |  |  | RD | Epic: Demo | [16 empty] | RD | [11 empty] | RD | RD |  |  | Yes | [7 empty] | Dropping SQL Server 2012
key |  |  | DevOps | Story: New | [16 empty] | DevOps | [11 empty] | DevOps | DevOps |  |  | Yes | [7 empty] | R&D Bucket
key |  |  | RD | Story: Review | [16 empty] | RD | [11 empty] | RD | RD |  |  | Yes | [7 empty] | Other
key |  |  | RD | Story: Ready | [16 empty] | RD | [15 empty] | Yes
key |  |  | RD | Story: In Development | [16 empty] | RD | [15 empty] | Yes
key |  |  | RD | Story: Validation | [32 empty] | Yes
key |  |  |  | Story: Demo Checkpoint | [32 empty] | Yes
key |  |  |  | Story: Done | [32 empty] | Yes
key |  |  |  | Story: In Development - On Hold | [32 empty] | Yes
key |  |  |  | Story: Demo Checkpoint - On Hold | [32 empty] | Yes
key |  |  |  | Story: Prototype Done | [32 empty] | Yes
key |  |  |  | Story: Ready for Validation | [32 empty] | Yes
key |  |  |  | Story: Validation - On Hold | [32 empty] | Yes
key |  |  |  | Story: Cancelled | [32 empty] | Yes
key |  |  |  | Tech Debt: New | [32 empty] | Yes
key |  |  |  | Tech Debt: Review | [32 empty] | Yes
key |  |  |  | Tech Debt: Ready | [32 empty] | Yes
key |  |  |  | Tech Debt: In Development | [32 empty] | Yes
key |  |  |  | Tech Debt: Validation | [32 empty] | Yes
key |  |  |  | Tech Debt: Demo Checkpoint | [32 empty] | Yes
key |  |  |  | Tech Debt: Done | [32 empty] | Yes
key |  |  |  | Tech Debt: In Development - On Hold | [32 empty] | Yes
key |  |  |  | Tech Debt: Demo Checkpoint - On Hold | [32 empty] | Yes
key |  |  |  | Tech Debt: Prototype Done | [32 empty] | Yes
key |  |  |  | Tech Debt: Ready for Validation | [32 empty] | Yes
key |  |  |  | Tech Debt: Validation - On Hold | [32 empty] | Yes
key |  |  |  | Tech Debt: Cancelled | [32 empty] | Yes
key |  |  |  | Bug: New | [32 empty] | Yes
key |  |  |  | Bug: Triage | [32 empty] | Yes
key |  |  |  | Bug: Ready | [32 empty] | Yes
key |  |  |  | Bug: In Development | [32 empty] | Yes
key |  |  |  | Bug: Validation | [32 empty] | Yes
key |  |  |  | Bug: Closed | [32 empty] | Yes
key |  |  |  | Bug: New - On Hold | [32 empty] | Yes
key |  |  |  | Bug: In Development - On Hold | [32 empty] | Yes
key |  |  |  | Bug: Validation - On Hold | [32 empty] | Yes
key |  |  |  | Bug: Investigate | [32 empty] | Yes
key |  |  |  | DevOps: New | [32 empty] | Yes
key |  |  |  | DevOps: Review | [32 empty] | Yes
key |  |  |  | DevOps: Ready | [32 empty] | Yes
key |  |  |  | DevOps: In Development | [32 empty] | Yes
key |  |  |  | DevOps: Validation | [32 empty] | Yes
key |  |  |  | DevOps: Demo Checkpoint | [32 empty] | Yes
key |  |  |  | DevOps: Done | [32 empty] | Yes
key |  |  |  | DevOps: In Development - On Hold | [32 empty] | Yes
key |  |  |  | DevOps: Demo Checkpoint - On Hold | [32 empty] | Yes
key |  |  |  | DevOps: Prototype Done | [32 empty] | Yes
key |  |  |  | DevOps: Ready for Validation | [32 empty] | Yes
key |  |  |  | DevOps: Validation - On Hold | [32 empty] | Yes
key |  |  |  | DevOps: Cancelled | [40 empty] | </jt:forEach>
key | [32 empty] | Unassigned