## Release
3400.25
70

## Reuse
200

## Glossary
200

## Doc Gen
200
200

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [7 empty] | Release, Reuse, Doc Gen | Glossary | Release | Reuse | Glossary | Doc Gen | Release |  | Reuse |  | Glossary |  | Doc Gen |  |  | Release | Titan
Actual | 86.96% | Start Date | End Date |  | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 13.04% | 2019-04-24 | 2019-07-30 | [5 empty] | 0% | 0% | 3% | 0% | 10% | 0% | 420 | 304 | 75 | 65 | 175 | 104 | 55 | 51 | 2019-05-20 | Not DevOps | Yes
|  |  | 2019-07-30 |  | T1 | 2019-04-24 | 2019-05-07 | 10 | 14.71% | 14.71% | 11% | 19% | 11% | 22% | 358.2353 | 369 | 63.9706 | 59 | 149.2647 | 169 | 46.9118 | 40 | 2019-07-01
Release |  | Report Date ??? | ${bpHelper.getToday()} |  | T2 | 2019-05-08 | 2019-05-21 | 9 | 27.94% | 27.94% | 31% | 31% | 35% | 90% | 302.6471 | 264 | 54.0441 | 57 | 126.1029 | 107 | 39.6324 | 4 |  | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Actual | 77.5% | Report Date | 2019-07-17 |  | T3 | 2019-05-22 | 2019-06-04 | 10 | 42.65% | 42.65% | 40% | 60% | 43% | 98% | 240.8824 | 277 | 43.0147 | 38 | 100.3676 | 110 | 31.5441 | 1 |  | (blank) | 1400.125
Remainder | 22.5% |  |  |  | T4 | 2019-06-05 | 2019-06-18 | 10 | 57.35% | 57.35% | 64% | 71% | 77% | 100% | 179.1176 | 153 | 31.9853 | 29 | 74.6324 | 39 | 23.4559 | 0 |  | Reuse | 200 | 150
[5 empty] | T5 | 2019-06-19 | 2019-07-02 | 9 | 70.59% | 70.59% | 74% | 98% | 85% | 100% | 123.5294 | 113 | 22.0588 | 2 | 51.4706 | 29 | 16.1765 | 0 |  | Glossary | 200 | 150
Reuse |  |  |  |  | T6 | 2019-07-03 | 2019-07-16 | 10 | 85.29% | 85.29% | 84% | 100% | 94% | 100% | 61.7647 | 72 | 11.0294 | 150 | 25.7353 | 11 | 8.0882 | 0 |  | Doc Gen | 200 | 150
Actual | 25% |  |  |  | T7 | 2019-07-17 | 2019-07-30 | 10 | 100% | 100% | 77.5% | 25% | 25% | 25% | 0 | 450 | 0 | 0 | 0 | 150 | 0 | 150 |  | Grand Total | 2000.125 | 450
Remainder | 75%
Glossary
Actual | 25%
Remainder | 75%
Doc Gen
Actual | 25%
Remainder | 75%
Time Elapsed Glossary
Actual | 86.96%
Remainder | 13.04%
|  | Release | Titan |  | Release | Titan |  | Release | Titan |  |  |  |  | Feature | Cost
Release | Titan | Type | Epic |  | Type | Epic |  | Type | Epic |  |  |  |  | Release | 420
Type | Epic | ST:Components | Reuse |  | ST:Components | Glossary |  | ST:Components | Doc Gen |  |  |  |  | Reuse | 75
Not DevOps | Yes | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  |  |  |  | Glossary | 175
[14 empty] | Doc Gen | 55
Values |  | Values |  |  | Values |  |  | Values
Done | 1550.125 | Done | 50 |  | Done | 50 |  | Done | 50
In Validation | 120 | In Validation | 40 |  | In Validation | 40 |  | In Validation | 40
In Dev | 180 | In Dev | 60 |  | In Dev | 60 |  | In Dev | 60
Ready | 90 | Ready | 30 |  | Ready | 30 |  | Ready | 30
Not Decomposed | 1460.125 | Not Decomposed | 20 |  | Not Decomposed | 20 |  | Not Decomposed | 20
Release | Titan
Type | Epic | Release | Titan |  | Release | Titan |  | Release | Titan
Not DevOps | Yes | Type | Epic |  | Type | Epic |  | Type | Epic
|  | ST:Components | Reuse |  | ST:Components | Glossary |  | ST:Components | Doc Gen
Sum of Epic Total Estimate
2000.125 | 3400.25 | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate
|  | 200 | 200 |  | 200 | 200 |  | 200 | 200
|  |  | Type | DevOps
Type | Epic
Release | Titan |  | Row Labels | Sum of Story Points
Not DevOps | Yes |  | Development/Internal Support | 10
|  |  | Planned - Deployment and Release | 10
Row Labels | Sum of Epic Total Estimate |  | Planned - Operational Efficiency | 10
Reuse | 600 |  | Planned - Platform Health | 10
Glossary | 200 |  | Planned - Security | 10
Doc Gen | 400 |  | Production Support | 10
R&D Bucket | 200 |  | Time Off / Conferences | 10
CI/CD | 200.125 |  | (blank)
DevOps | 200 |  | Grand Total | 70
Other | 200
Grand Total | 2000.125
| 2000.125 |  |  | 70

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | Reuse | [7 empty] | Glossary | [7 empty] | Doc Gen
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
|  |  | 315 | 420 | 290 | 252 | 11 | 304 | 80% | 3.492% | 65 | 75 | 65 | 65 | 0 | 65 | 100% | 0% | 115 | 175 | 90 | 72 | 11 | 104 | 62.61% | 9.565% | 51 | 55 | 51 | 51 | 0 | 51 | 100% | 0%
T1 | 2019-04-24 | 2019-05-07 | 416.5 | 420 | 326.5 | 286.5 | 47.5 | 369 | 68.79% | 11.4% | 73 | 75 | 73 | 65 | 14 | 59 | 89.04% | 19.18% | 190 | 175 | 110 | 100 | 21 | 169 | 52.63% | 11.05% | 51 | 55 | 51 | 51 | 11 | 40 | 100% | 21.57%
T2 | 2019-05-08 | 2019-05-21 | 385 | 420 | 375 | 332 | 121 | 264 | 86.23% | 31.43% | 83 | 75 | 83 | 70 | 26 | 57 | 84.34% | 31.33% | 164 | 175 | 164 | 154 | 57 | 107 | 93.9% | 34.76% | 40 | 55 | 40 | 40 | 36 | 4 | 100% | 90%
T3 | 2019-05-22 | 2019-06-04 | 463 | 420 | 452 | 406 | 186 | 277 | 87.69% | 40.17% | 94 | 75 | 94 | 81 | 56 | 38 | 86.17% | 59.57% | 192 | 175 | 192 | 184 | 82 | 110 | 95.83% | 42.71% | 41 | 55 | 41 | 41 | 40 | 1 | 100% | 97.56%
T4 | 2019-06-05 | 2019-06-18 | 422 | 420 | 411 | 390 | 269 | 153 | 92.42% | 63.74% | 101 | 75 | 101 | 85 | 72 | 29 | 84.16% | 71.29% | 173 | 175 | 173 | 173 | 134 | 39 | 100% | 77.46% | 41 | 55 | 41 | 41 | 41 | 0 | 100% | 100% | Release | Titan
T5 | 2019-06-19 | 2019-07-02 | 439.5 | 420 | 438.5 | 424.5 | 326.5 | 113 | 96.59% | 74.29% | 92 | 75 | 92 | 90 | 90 | 2 | 97.83% | 97.83% | 192.5 | 175 | 192.5 | 192.5 | 163.5 | 29 | 100% | 84.94% | 41 | 55 | 41 | 41 | 41 | 0 | 100% | 100% | Not DevOps | Yes
T6 | 2019-07-03 | 2019-07-16 | 446.5 | 420 | 446.5 | 439.5 | 374.5 | 72 | 98.43% | 83.87% | 91.5 | 75 | 91.5 | 91.5 | 91.5 | 0 | 100% | 100% | 190.5 | 175 | 190.5 | 190.5 | 179.5 | 11 | 100% | 94.23% | 41 | 55 | 41 | 41 | 41 | 0 | 100% | 100%
T7 | 2019-07-17 | 2019-07-30 | 2000.125 | 420 | 0 | 540 | 1550.125 | 450 | 27% | 77.5% | 200 | 75 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 175 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 55 | 0 | 180 | 50 | 150 | 90% | 25% |  | Column Labels
Epic
[35 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
[35 empty] | (blank) | 1400.125
[35 empty] | Reuse | 200 |  | 180 | 150
[35 empty] | Glossary | 200 |  | 180 | 150
[35 empty] | Doc Gen | 200 |  | 180 | 150
[35 empty] | Grand Total | 2000.125 |  | 540 | 450

## _ReadinessData (hidden)
Not DevOps | Yes
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate |  | Not DevOps | Yes
Epic | 1460.125
Grand Total | 1460.125 |  | Row Labels | Sum of Story Points
|  |  | (blank) | 20
|  |  | RD | 15
|  |  | Grand Total | 35
Sprint | Epics New | Stories Ready
T1 | 135 | 192
T2 | 57 | 153
T3 | 60 | 119
T4 | 35 | 61
T5 | 18 | 44
T6 | 199 | 25
T7 | 1460.125 | 35

## Team Backlog
490

## _TeamBacklogData (hidden)
Release | Titan
Type | (Multiple Items)
Team Grouped | (All)
Not DevOps | Yes
Row Labels | Sum of Story Points
Closed | 100
Validation | 100
In Dev | 100
Ready | 100
New | 90
Grand Total | 490
Grand Total | 490

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Not DevOps | Yes
Row Labels | Sum of Story Points | Historical
T1 | 100 | Sprint | R&D | Total
T2 | 60 | T1 | 46.25
T3 | 30 | T2 | 80.75
T4 | 60 | T3 | 69
T5 | 60 | T4 | 91
T6 | 60 | T5 | 69
Grand Total | 370 | T6 | 54.5
T7
|  | Total | 410.5 | 0

## Active Sprint
16

## _ActiveSprintData (hidden)
Active Sprint | Titan7 | Type | (Multiple Items)
|  | Last Sprint | Titan7
|  | Not DevOps | Yes
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 1
|  | New | 1
|  | Cancelled | 1
Unkown
|  | (blank) | 10
|  | Grand Total | 16
|  | Grand Total | 16
|  | Chart Total | Sprint Titan7 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()} |  |  | Total P0/P1 Bugs: ${bpHelper.getTotalP0P1BugCount()}
Custom P0/P1 Bugs: ${bpHelper.getCustomP0P1BugCount()}
| Release | Titan
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Titan
| Type | Bug
| Team Grouped | (All)
| Status | Bug: Closed
| Row Labels | Count of Key
| T1 | 1
T2
T3
| T4 | 1
T5
T6
T7
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Titan Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | DevOps Type | Not DevOps | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-titan-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(AE2, "itan", ""), "aturn", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getTitanComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.getDevOpsType(issue)} | $[IF(K2="DevOps","","Yes")] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | RD | Epic: New | [16 empty] | RD | [8 empty] | Titan1 |  | Titan |  | New | Doc Gen |  | RD | RD | [6 empty] | Yes
key | Story |  | RD | Epic: Decomposition | [8 empty] | 5 | [7 empty] | RD | [8 empty] | Titan2 |  |  |  | Ready | Reuse |  | RD | RD | [6 empty] | Yes | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | RD | Epic: Review | [8 empty] | 10 | [7 empty] | RD | [8 empty] | Titan3 |  |  |  | In Dev | Glossary |  | RD | RD | [6 empty] | Yes | Yes
key | Tech Debt |  | RD | Epic: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Titan4 |  |  |  | Validation | DevOps |  | RD | RD | [7 empty] | Yes
key | Bug |  | RD | Epic: In Development | [16 empty] | RD | [8 empty] | Titan5 |  |  |  | Closed | R&D Bucket |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Titan6 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Cancelled | [16 empty] | RD | [8 empty] | Titan7 |  |  |  | Unkown |  |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Demo | [16 empty] | RD | [8 empty] | Titan2 | [6 empty] | RD | RD | [6 empty] | Yes
key | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Titan3 | T1 | [5 empty] | DevOps | DevOps | [6 empty] | Yes
key |  |  | RD | Story: Review | [16 empty] | RD | [8 empty] | Titan4 | T2 | [13 empty] | Yes
key | Story |  | RD | Story: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Titan5 | T3 | [13 empty] | Yes | Yes
key |  |  | RD | Story: In Development | [16 empty] | RD | [8 empty] | Titan6 | T4 | [13 empty] | Yes
key | DevOps |  |  | Story: Validation | [8 empty] | 10 | [16 empty] | Titan1 | T5 | [12 empty] | Development/Internal Support | Yes
key | DevOps |  |  | Story: Demo Checkpoint | [8 empty] | 10 | [16 empty] | Titan7 | T6 | [12 empty] | Production Support | Yes
key | DevOps |  |  | Story: Done | [8 empty] | 10 | [16 empty] | Titan3 | T1 | [12 empty] | Planned - Deployment and Release | Yes
key | DevOps |  |  | Story: In Development - On Hold | [8 empty] | 10 | [16 empty] | Titan4 | T2 | [12 empty] | Planned - Operational Efficiency | Yes
key | DevOps |  |  | Story: Demo Checkpoint - On Hold | [8 empty] | 10 | [16 empty] | Titan5 | T3 | [12 empty] | Planned - Platform Health | Yes
key | DevOps |  |  | Story: Prototype Done | [8 empty] | 10 | [16 empty] | Titan6 | T4 | [12 empty] | Planned - Security | Yes
key | DevOps |  |  | Story: Ready for Validation | [8 empty] | 10 | [16 empty] | Titan1 | T5 | [12 empty] | Time Off / Conferences | Yes
key |  |  |  | Story: Validation - On Hold | [25 empty] | Titan2 | T6 | [13 empty] | Yes
key |  |  |  | Story: Cancelled | [25 empty] | Titan7 | T1 | [13 empty] | Yes
key |  |  |  | Tech Debt: New | [25 empty] | Titan4 | T1 | [13 empty] | Yes
key |  |  |  | Tech Debt: Review | [40 empty] | Yes
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30 | [31 empty] | Yes
key |  |  |  | Tech Debt: In Development | [27 empty] | Saturn | [12 empty] | Yes
key |  |  |  | Tech Debt: Validation | [40 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | New | [10 empty] | Yes
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | Ready | [10 empty] | Yes
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | In Dev | [10 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | Validation | [10 empty] | Yes
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | Closed | [10 empty] | Yes
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | Cancelled | [10 empty] | Yes
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Titan7 |  |  |  | Unkown | [10 empty] | Yes
key |  |  |  | Tech Debt: Cancelled | [25 empty] | Titan1 | [14 empty] | Yes
key |  |  |  | Bug: New | [40 empty] | Yes
key |  |  |  | Bug: Triage | [40 empty] | Yes
key | Bug |  |  | Bug: Ready | [26 empty] | T1 | Titan | Highest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development | [26 empty] | T2 | Titan | High |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Validation | [26 empty] | T3 | Titan | Medium |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | T4 | Titan | Low |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: New - On Hold | [26 empty] | T5 | Titan | Lowest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | T6 | Titan | Low |  |  |  | RD | [7 empty] | Yes
key | bug |  |  | Bug: Validation - On Hold | [26 empty] | T7 | Titan | [12 empty] | Yes
key |  |  |  | Bug: Investigate | [40 empty] | Yes
key | [44 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | T1 | Titan | Highest |  |  |  | RD | [7 empty] | Yes
key | Epic | [8 empty] | Reuse |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Titan |  |  | DevOps |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic | [8 empty] | Glossary |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Titan |  |  | Reuse |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic |  |  | Story: New | [5 empty] | Doc Gen |  |  | 10 |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Titan |  | New | Doc Gen |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Story |  |  | Story: Ready | [5 empty] | Doc Gen |  |  | 10 |  | 200 | 150 | [15 empty] | Titan |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [5 empty] | Doc Gen |  |  | 10 |  | 200 | 150 | [15 empty] | Titan |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Titan |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Titan |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Titan |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Titan |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Titan |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Titan |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Titan |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Titan |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Titan |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Titan |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Titan |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Titan |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Titan |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Titan |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Titan |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Titan |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Titan |  | Closed |  |  | RD | [7 empty] | Yes
key | [44 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Titan |  |  | Doc Gen | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Titan |  |  | Reuse | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Titan |  |  | R&D Bucket | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Titan |  |  | Other | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Titan |  |  | Glossary | [9 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200 | [15 empty] | T1 | Titan |  |  | DevOps |  | NW
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200.125 | [15 empty] | T2 | Titan |  |  | CI/CD |  | ngStars | [7 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200 | [15 empty] | T3 | Titan |  |  | Reuse |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T4 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T5 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T6 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T1 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T2 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T3 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T4 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T5 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T6 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T1 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T2 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | T1 | [13 empty] | Yes
key | DevOps |  |  | DevOps: New | [40 empty] | Yes
key | DevOps |  |  | DevOps: Review | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint | [40 empty] | Yes
key | DevOps |  |  | DevOps: Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Prototype Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready for Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Cancelled | [40 empty] | Yes | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).