## Release
600
70

## Admin
0

## Visio Import
-100

## BoA Audit
-100
-100

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [7 empty] | Release, Admin, Visio Import | Excel Export | Release | Admin | Visio Import | Excel Export | Release |  | Admin |  | Visio Import |  | Excel Export |  |  | Release | Wavelength
Actual | 1.471% | Start Date | End Date |  | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 98.53% | 2020-02-12 | 2020-05-19 | [5 empty] | 0% | 0% | 11% | 29% | 0% | 0% | 470 | 465 | 200 | 136 | 200 | 178 | 60 | 59 | 2020-02-17 | Not DevOps | Yes
|  |  | 2020-05-19 |  | W1 | 2020-02-12 | 2020-02-25 | 9 | 13.43% | 13.43% | 25% | -50% | -200% | -200% | 406.8657 | 450 | 173.1343 | 150 | 173.1343 | 150 | 51.9403 | 150 | 2020-04-10
Release |  | Report Date ??? | ${bpHelper.getToday()} |  | W2 | 2020-02-26 | 2020-03-10 | 10 | 28.36% | 28.36% |  |  |  |  | 336.7164 |  | 143.2836 |  | 143.2836 |  | 42.9851 |  | 2020-05-18 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Actual | 25% | Report Date | 2020-02-12 |  | W3 | 2020-03-11 | 2020-03-24 | 10 | 43.28% | 43.28% |  |  |  |  | 266.5672 |  | 113.4328 |  | 113.4328 |  | 34.0299 |  |  | (blank) | 400
Remainder | 75% |  |  |  | W4 | 2020-03-25 | 2020-04-07 | 10 | 58.21% | 58.21% |  |  |  |  | 196.4179 |  | 83.5821 |  | 83.5821 |  | 25.0746 |  |  | Admin | 100 | 150
[5 empty] | W5 | 2020-04-08 | 2020-04-21 | 9 | 71.64% | 71.64% |  |  |  |  | 133.2836 |  | 56.7164 |  | 56.7164 |  | 17.0149 |  |  | Visio Import/Export | 50 | 150
Admin |  |  |  |  | W6 | 2020-04-22 | 2020-05-05 | 10 | 86.57% | 86.57% |  |  |  |  | 63.1343 |  | 26.8657 |  | 26.8657 |  | 8.0597 |  |  | Logging and Audit | 50 | 150
Actual | -50% |  |  |  | W7 | 2020-05-06 | 2020-05-19 | 9 | 100% | 100% |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Grand Total | 600 | 450
Remainder | 150%
Visio Import
Actual | -200%
Remainder | 300%
BoA Audit
Actual | -200%
Remainder | 300%
Time Elapsed BoA Audit
Actual | 1.471%
Remainder | 98.53%
|  | Release | Wavelength |  | Release | Wavelength |  | Release | Wavelength |  |  |  |  | Feature | Cost
Release | Wavelength | Type | Epic |  | Type | Epic |  | Type | Epic |  |  |  |  | Release | 470
Type | Epic | ST:Components | Admin |  | ST:Components | Visio Import/Export |  | ST:Components | Logging and Audit |  |  |  |  | Admin | 200
Not DevOps | Yes | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  |  |  |  | Visio Import | 200
[14 empty] | BoA Audit | 60
Values |  | Values |  |  | Values |  |  | Values
Done | 150 | Done | -50 |  | Done | -100 |  | Done | -100
In Validation | 120 | In Validation | 40 |  | In Validation | 40 |  | In Validation | 40
In Dev | 180 | In Dev | 60 |  | In Dev | 60 |  | In Dev | 60
Ready | 90 | Ready | 30 |  | Ready | 30 |  | Ready | 30
Not Decomposed | 60 | Not Decomposed | -80 |  | Not Decomposed | -130 |  | Not Decomposed | -130
Release | Wavelength
Type | Epic | Release | Wavelength |  | Release | Wavelength |  | Release | Wavelength
Not DevOps | Yes | Type | Epic |  | Type | Epic |  | Type | Epic
|  | ST:Components | Admin |  | ST:Components | Visio Import/Export |  | ST:Components | Logging and Audit
Sum of Epic Total Estimate
600 | 600 | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate
|  | 100 | 0 |  | 50 | -100 |  | 50 | -100
|  |  | Type | DevOps
Type | Epic
Release | Wavelength |  | Row Labels | Sum of Story Points
Not DevOps | Yes |  | Development/Internal Support | 10
|  |  | Planned - Deployment and Release | 10
Row Labels | Sum of Epic Total Estimate |  | Planned - Operational Efficiency | 10
Admin | 250 |  | Planned - Platform Health | 10
Visio Import | 100 |  | Planned - Security | 10
BoA Audit | 150 |  | Production Support | 10
R&D Bucket | 50 |  | Time Off / Conferences | 10
Other | 50 |  | (blank)
Grand Total | 600 |  | Grand Total | 70
| 600 |  |  | 70

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | Admin | [7 empty] | Visio Import | [7 empty] | BoA Audit
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
|  |  | 520.8 | 470 | 443.8 | 378.3 | 55.8 | 465 | 72.64% | 10.71% | 191.8 | 200 | 124.8 | 120.8 | 55.8 | 136 | 62.98% | 29.09% | 178 | 200 | 178 | 117 | 0 | 178 | 65.73% | 0% | 59 | 60 | 59 | 59 | 0 | 59 | 100% | 0%
W1 | 2020-02-12 | 2020-02-25 | 600 | 470 | 0 | 540 | 150 | 450 | 90% | 25% | 100 | 200 | 0 | 180 | -50 | 150 | 180% | -50% | 50 | 200 | 0 | 180 | -100 | 150 | 360% | -200% | 50 | 60 | 0 | 180 | -100 | 150 | 360% | -200%
W2 | 2020-02-26 | 2020-03-10 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0!
W3 | 2020-03-11 | 2020-03-24 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0!
W4 | 2020-03-25 | 2020-04-07 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | Release | Wavelength
W5 | 2020-04-08 | 2020-04-21 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | Not DevOps | Yes
W6 | 2020-04-22 | 2020-05-05 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0!
W7 | 2020-05-06 | 2020-05-19 | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | #DIV/0! |  | Column Labels
Epic
[35 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
[35 empty] | (blank) | 400
[35 empty] | Admin | 100 |  | 180 | 150
[35 empty] | Visio Import/Export | 50 |  | 180 | 150
[35 empty] | Logging and Audit | 50 |  | 180 | 150
[35 empty] | Grand Total | 600 |  | 540 | 450

## _ReadinessData (hidden)
Not DevOps | Yes
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate |  | Not DevOps | Yes
Epic | 60
Grand Total | 60 |  | Row Labels | Sum of Story Points
|  |  | (blank) | 20
|  |  | RD | 15
|  |  | Grand Total | 35
Sprint | Epics New | Stories Ready
W1 | 60 | 35
W2
W3
W4
W5
W6
W7

## Team Backlog
490

## _TeamBacklogData (hidden)
Release | Wavelength
Type | (Multiple Items)
Team Grouped | (All)
Not DevOps | Yes
Row Labels | Sum of Story Points
Closed | 100
Validation | 100
In Dev | 100
Ready | 100
New | 90
Grand Total | 490
Grand Total | 490

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Not DevOps | Yes
Row Labels | Sum of Story Points | Historical
W1 | 100 | Sprint | R&D | Total
W2 | 60 | W1
W3 | 30 | W2
W4 | 60 | W3
W5 | 60 | W4
W6 | 60 | W5
W7 |  | W6
Grand Total | 370 | W7
|  | Total | 0 | 0

## Active Sprint
26

## _ActiveSprintData (hidden)
Active Sprint | Wavelength1 | Type | (Multiple Items)
|  | Last Sprint | Wavelength1
|  | Not DevOps | Yes
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 1
|  | New | 1
|  | Cancelled | 1
|  | (blank) | 20
|  | Grand Total | 26
|  | Grand Total | 26
|  | Chart Total | Sprint Wavelength1 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()} |  |  | Total P0/P1 Bugs: ${bpHelper.getTotalP0P1BugCount()}
Custom P0/P1 Bugs: ${bpHelper.getCustomP0P1BugCount()}
| Release | Wavelength
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Wavelength
| Type | Bug
| Team Grouped | (All)
| Status | Bug: Closed
| Row Labels | Count of Key
| W1 | 1
W2
W3
| W4 | 1
W5
W6
W7
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Release Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | DevOps Type | Not DevOps | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-wavelength-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(AE2, "avelength", ""), "enus", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getWavelengthComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.getDevOpsType(issue)} | $[IF(K2="DevOps","","Yes")] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | RD | Epic: New | [16 empty] | RD | [8 empty] | Wavelength1 |  | Venus |  | New | Visio Import |  | RD | RD | [6 empty] | Yes
key | Story |  | RD | Epic: Decomposition | [8 empty] | 5 | [7 empty] | RD | [8 empty] | Wavelength2 |  |  |  | Ready | Admin |  | RD | RD | [6 empty] | Yes | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | RD | Epic: Review | [8 empty] | 10 | [7 empty] | RD | [8 empty] | Wavelength3 |  |  |  | In Dev | BoA Audit |  | RD | RD | [6 empty] | Yes | Yes
key | Tech Debt |  | RD | Epic: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Wavelength4 |  |  |  | Validation | DevOps |  | RD | RD | [7 empty] | Yes
key | Bug |  | RD | Epic: In Development | [16 empty] | RD | [8 empty] | Wavelength5 |  |  |  | Closed | R&D Bucket |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Wavelength6 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Cancelled | [16 empty] | RD | [8 empty] | Wavelength7 |  |  |  | Unkown |  |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Demo | [16 empty] | RD | [8 empty] | Wavelength2 | [6 empty] | RD | RD | [6 empty] | Yes
key | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Wavelength3 | W1 | [5 empty] | DevOps | DevOps | [6 empty] | Yes
key |  |  | RD | Story: Review | [16 empty] | RD | [8 empty] | Wavelength4 | W2 | [13 empty] | Yes
key | Story |  | RD | Story: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Wavelength5 | W3 | [13 empty] | Yes | Yes
key |  |  | RD | Story: In Development | [16 empty] | RD | [8 empty] | Wavelength6 | W4 | [13 empty] | Yes
key | DevOps |  |  | Story: Validation | [8 empty] | 10 | [16 empty] | Wavelength1 | W5 | [12 empty] | Development/Internal Support | Yes
key | DevOps |  |  | Story: Demo Checkpoint | [8 empty] | 10 | [16 empty] | Wavelength7 | W6 | [12 empty] | Production Support | Yes
key | DevOps |  |  | Story: Done | [8 empty] | 10 | [16 empty] | Wavelength3 | W1 | [12 empty] | Planned - Deployment and Release | Yes
key | DevOps |  |  | Story: In Development - On Hold | [8 empty] | 10 | [16 empty] | Wavelength4 | W2 | [12 empty] | Planned - Operational Efficiency | Yes
key | DevOps |  |  | Story: Demo Checkpoint - On Hold | [8 empty] | 10 | [16 empty] | Wavelength5 | W3 | [12 empty] | Planned - Platform Health | Yes
key | DevOps |  |  | Story: Prototype Done | [8 empty] | 10 | [16 empty] | Wavelength6 | W4 | [12 empty] | Planned - Security | Yes
key | DevOps |  |  | Story: Ready for Validation | [8 empty] | 10 | [16 empty] | Wavelength1 | W5 | [12 empty] | Time Off / Conferences | Yes
key |  |  |  | Story: Validation - On Hold | [25 empty] | Wavelength2 | W6 | [13 empty] | Yes
key |  |  |  | Story: Cancelled | [25 empty] | Wavelength7 | W1 | [13 empty] | Yes
key |  |  |  | Tech Debt: New | [25 empty] | Wavelength4 | W1 | [13 empty] | Yes
key |  |  |  | Tech Debt: Review | [40 empty] | Yes
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30 | [31 empty] | Yes
key |  |  |  | Tech Debt: In Development | [27 empty] | Venus | [12 empty] | Yes
key |  |  |  | Tech Debt: Validation | [40 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | New | [10 empty] | Yes
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | Ready | [10 empty] | Yes
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | In Dev | [10 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | Validation | [10 empty] | Yes
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | Closed | [10 empty] | Yes
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | Cancelled | [10 empty] | Yes
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Wavelength1 |  |  |  | Unkown | [10 empty] | Yes
key |  |  |  | Tech Debt: Cancelled | [25 empty] | Wavelength1 | [14 empty] | Yes
key |  |  |  | Bug: New | [40 empty] | Yes
key |  |  |  | Bug: Triage | [40 empty] | Yes
key | Bug |  |  | Bug: Ready | [26 empty] | W1 | Wavelength | Highest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development | [26 empty] | W2 | Wavelength | High |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Validation | [26 empty] | W3 | Wavelength | Medium |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | W4 | Wavelength | Low |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: New - On Hold | [26 empty] | W5 | Wavelength | Lowest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | W6 | Wavelength | Low |  |  |  | RD | [7 empty] | Yes
key | bug |  |  | Bug: Validation - On Hold | [26 empty] | W7 | Wavelength | [12 empty] | Yes
key |  |  |  | Bug: Investigate | [40 empty] | Yes
key | [44 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | W1 | Wavelength | Highest |  |  |  | RD | [7 empty] | Yes
key | Epic | [8 empty] | Admin |  |  |  |  | 100 | 150 | [5 empty] | 180 | [9 empty] | Wavelength |  |  | Admin |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic | [8 empty] | Visio Import/Export |  |  |  |  | 50 | 150 | [5 empty] | 180 | [9 empty] | Wavelength |  |  | Admin |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic |  |  | Story: New | [5 empty] | Logging and Audit |  |  | 10 |  | 50 | 150 | [5 empty] | 180 | [9 empty] | Wavelength |  | New | BoA Audit |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Story |  |  | Story: Ready | [5 empty] | Logging and Audit |  |  | 10 |  | 50 | 150 | [15 empty] | Wavelength |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [5 empty] | Logging and Audit |  |  | 10 |  | 750 | 150 | [15 empty] | Wavelength |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Wavelength |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Wavelength |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Wavelength |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Wavelength |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Wavelength |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Wavelength |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Wavelength |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Wavelength |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Wavelength |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Wavelength |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Wavelength |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Wavelength |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Wavelength |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Wavelength |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Wavelength |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Wavelength |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Wavelength |  | Closed |  |  | RD | [7 empty] | Yes
key | [44 empty] | Yes
key | Epic | [13 empty] | 100 | [16 empty] | Wavelength |  |  | BoA Audit | [9 empty] | Yes
key | Epic | [13 empty] | 50 | [16 empty] | Wavelength |  |  | Admin | [9 empty] | Yes
key | Epic | [13 empty] | 50 | [16 empty] | Wavelength |  |  | R&D Bucket | [9 empty] | Yes
key | Epic | [13 empty] | 50 | [16 empty] | Wavelength |  |  | Other | [9 empty] | Yes
key | Epic | [13 empty] | 50 | [16 empty] | Wavelength |  |  | Visio Import | [9 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | W1 | Wavelength |  |  | Admin |  | NW
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | W2 | Wavelength |  |  | Visio Import |  | ngStars | [7 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | W3 | Wavelength |  |  | Admin |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W4 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W5 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W6 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W1 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W2 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W3 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W4 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W5 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W6 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W1 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W2 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | W1 | [13 empty] | Yes
key | DevOps |  |  | DevOps: New | [40 empty] | Yes
key | DevOps |  |  | DevOps: Review | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint | [40 empty] | Yes
key | DevOps |  |  | DevOps: Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Prototype Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready for Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Cancelled | [40 empty] | Yes | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).