## Release
3400.25
70

## Version Compare
200

## Traces
200

## Process Artifact
200
200

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [7 empty] | Release, Version Compare, Process Artifact | Glossary | Release | Version Compare | Traces | Process Artifact | Release |  | Version Compare |  | Traces |  | Process Artifact |  |  | Release | Ursa
Actual | 95.52% | Start Date | End Date |  | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 4.478% | 2019-07-31 | 2019-11-05 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 420 | 435 | 150 | 148 | 120 | 118 | 55 | 55 | 2019-08-05 | Not DevOps | Yes
|  |  | 2019-11-05 |  | U1 | 2019-07-31 | 2019-08-13 | 9 | 13.43% | 13.43% | 13% | 6% | 19% | 29% | 363.5821 | 391 | 129.8507 | 137 | 103.8806 | 97 | 47.6119 | 39 | 2019-09-02
Release |  | Report Date ??? | ${bpHelper.getToday()} |  | U2 | 2019-08-14 | 2019-08-27 | 10 | 28.36% | 28.36% | 32% | 29% | 48% | 54% | 300.8955 | 298 | 107.4627 | 100 | 85.9701 | 61 | 39.403 | 24 | 2019-10-14 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Actual | 77.5% | Report Date | 2019-10-31 |  | U3 | 2019-08-28 | 2019-09-10 | 9 | 41.79% | 41.79% | 50% | 63% | 55% | 79% | 244.4776 | 214 | 87.3134 | 49 | 69.8507 | 53 | 32.0149 | 11 |  | (blank) | 1400.125
Remainder | 22.5% |  |  |  | U4 | 2019-09-11 | 2019-09-24 | 10 | 56.72% | 56.72% | 57% | 67% | 65% | 89% | 181.791 | 195 | 64.9254 | 45 | 51.9403 | 42 | 23.806 | 6 |  | Version Compare | 200 | 150
[5 empty] | U5 | 2019-09-25 | 2019-10-08 | 10 | 71.64% | 71.64% | 75% | 86% | 82% | 100% | 119.1045 | 110 | 42.5373 | 18 | 34.0299 | 26 | 15.597 | 0 |  | Traces | 200 | 150
Version Compare |  |  |  |  | U6 | 2019-10-09 | 2019-10-22 | 9 | 85.07% | 85.07% | 88% | 96% | 100% | 100% | 62.6866 | 53 | 22.3881 | 5 | 17.9104 | 0 | 8.209 | 0 |  | Process Artifact | 200 | 150
Actual | 25% |  |  |  | U7 | 2019-10-23 | 2019-11-05 | 10 | 100% | 100% | 77.5% | 25% | 25% | 25% | 0 | 450 | 0 | 150 | 0 | 150 | 0 | 150 |  | Grand Total | 2000.125 | 450
Remainder | 75%
Traces
Actual | 25%
Remainder | 75%
Process Artifact
Actual | 25%
Remainder | 75%
Time Elapsed Glossary
Actual | 95.52%
Remainder | 4.478%
|  | Release | Ursa |  | Release | Ursa |  | Release | Ursa |  |  |  |  | Feature | Cost
Release | Ursa | Type | Epic |  | Type | Epic |  | Type | Epic |  |  |  |  | Release | 420
Type | Epic | ST:Components | Version Compare |  | ST:Components | Traces |  | ST:Components | Process Artifact |  |  |  |  | Version Compare | 150
Not DevOps | Yes | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  |  |  |  | Traces | 120
[14 empty] | Process Artifact | 55
Values |  | Values |  |  | Values |  |  | Values
Done | 1550.125 | Done | 50 |  | Done | 50 |  | Done | 50
In Validation | 120 | In Validation | 40 |  | In Validation | 40 |  | In Validation | 40
In Dev | 180 | In Dev | 60 |  | In Dev | 60 |  | In Dev | 60
Ready | 90 | Ready | 30 |  | Ready | 30 |  | Ready | 30
Not Decomposed | 1460.125 | Not Decomposed | 20 |  | Not Decomposed | 20 |  | Not Decomposed | 20
Release | Ursa
Type | Epic | Release | Ursa |  | Release | Ursa |  | Release | Ursa
Not DevOps | Yes | Type | Epic |  | Type | Epic |  | Type | Epic
|  | ST:Components | Version Compare |  | ST:Components | Traces |  | ST:Components | Process Artifact
Sum of Epic Total Estimate
2000.125 | 3400.25 | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate
|  | 200 | 200 |  | 200 | 200 |  | 200 | 200
|  |  | Type | DevOps
Type | Epic
Release | Ursa |  | Row Labels | Sum of Story Points
Not DevOps | Yes |  | Development/Internal Support | 10
|  |  | Planned - Deployment and Release | 10
Row Labels | Sum of Epic Total Estimate |  | Planned - Operational Efficiency | 10
Version Compare | 600 |  | Planned - Platform Health | 10
Traces | 200 |  | Planned - Security | 10
Process Improvements | 400 |  | Production Support | 10
R&D Bucket | 200 |  | Time Off / Conferences | 10
Other | 200 |  | (blank)
Grand Total | 1600 |  | Grand Total | 70
| 1600 |  |  | 70

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | Version Compare | [7 empty] | Traces | [7 empty] | Process Artifact
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
|  |  | 435 | 420 | 435 | 350 | 0 | 435 | 80.46% | 0% | 148 | 150 | 148 | 148 | 0 | 148 | 100% | 0% | 118 | 120 | 118 | 103 | 0 | 118 | 87.29% | 0% | 55 | 55 | 55 | 55 | 0 | 55 | 100% | 0%
U1 | 2019-07-31 | 2019-08-13 | 448 | 420 | 448 | 375 | 57 | 391 | 83.71% | 12.72% | 146 | 150 | 146 | 146 | 9 | 137 | 100% | 6.164% | 120 | 120 | 120 | 120 | 23 | 97 | 100% | 19.17% | 55 | 55 | 55 | 55 | 16 | 39 | 100% | 29.09%
U2 | 2019-08-14 | 2019-08-27 | 440 | 420 | 440 | 373 | 142 | 298 | 84.77% | 32.27% | 141 | 150 | 141 | 141 | 41 | 100 | 100% | 29.08% | 118 | 120 | 118 | 118 | 57 | 61 | 100% | 48.31% | 52 | 55 | 52 | 52 | 28 | 24 | 100% | 53.85%
U3 | 2019-08-28 | 2019-09-10 | 430 | 420 | 430 | 379 | 216 | 214 | 88.14% | 50.23% | 131 | 150 | 131 | 131 | 82 | 49 | 100% | 62.6% | 118 | 120 | 118 | 118 | 65 | 53 | 100% | 55.08% | 52 | 55 | 52 | 52 | 41 | 11 | 100% | 78.85%
U4 | 2019-09-11 | 2019-09-24 | 449 | 420 | 449 | 449 | 254 | 195 | 100% | 56.57% | 137 | 150 | 137 | 137 | 92 | 45 | 100% | 67.15% | 120 | 120 | 120 | 120 | 78 | 42 | 100% | 65% | 52.5 | 55 | 52.5 | 52.5 | 46.5 | 6 | 100% | 88.57% | Release | Ursa
U5 | 2019-09-25 | 2019-10-08 | 440.5 | 420 | 440.5 | 440.5 | 330.5 | 110 | 100% | 75.03% | 129 | 150 | 129 | 129 | 111 | 18 | 100% | 86.05% | 141 | 120 | 141 | 141 | 115 | 26 | 100% | 81.56% | 48.5 | 55 | 48.5 | 48.5 | 48.5 | 0 | 100% | 100% | Not DevOps | Yes
U6 | 2019-10-09 | 2019-10-22 | 440 | 420 | 440 | 440 | 387 | 53 | 100% | 87.95% | 133.5 | 150 | 133.5 | 133.5 | 128.5 | 5 | 100% | 96.25% | 140 | 120 | 140 | 140 | 140 | 0 | 100% | 100% | 48.4 | 55 | 48.5 | 48.5 | 48.4 | 0 | 100.2% | 100%
U7 | 2019-10-23 | 2019-11-05 | 2000.125 | 420 | 0 | 540 | 1550.125 | 450 | 27% | 77.5% | 200 | 150 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 120 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 55 | 0 | 180 | 50 | 150 | 90% | 25% |  | Column Labels
Epic
[35 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
[35 empty] | (blank) | 1400.125
[35 empty] | Version Compare | 200 |  | 180 | 150
[35 empty] | Traces | 200 |  | 180 | 150
[35 empty] | Process Artifact | 200 |  | 180 | 150
[35 empty] | Grand Total | 2000.125 |  | 540 | 450

## _ReadinessData (hidden)
Not DevOps | Yes
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate |  | Not DevOps | Yes
Epic | 1460.125
Grand Total | 1460.125 |  | Row Labels | Sum of Story Points
|  |  | (blank) | 20
|  |  | RD | 15
|  |  | Grand Total | 35
Sprint | Epics New | Stories Ready
T1 | 74 | 239
T2 | 67 | 177
T3 | 51 | 144
T4 | 0 | 150
T5 | 241 | 224
T6 | 120 | 321
T7 | 1460.125 | 35

## Team Backlog
490

## _TeamBacklogData (hidden)
Release | Ursa
Type | (Multiple Items)
Team Grouped | (All)
Not DevOps | Yes
Row Labels | Sum of Story Points
Closed | 100
Validation | 100
In Dev | 100
Ready | 100
New | 90
Grand Total | 490
Grand Total | 490

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Not DevOps | Yes
Row Labels | Sum of Story Points | Historical
U1 | 100 | Sprint | R&D | Total
U2 | 60 | T1 | 62.5
U3 | 30 | T2 | 88
U4 | 60 | T3 | 77
U5 | 60 | T4 | 40.5
U6 | 60 | T5 | 85.5
U7 |  | T6 | 80
Grand Total | 370 | T7
|  | Total | 433.5 | 0

## Active Sprint
16

## _ActiveSprintData (hidden)
Active Sprint | Ursa7 | Type | (Multiple Items)
|  | Last Sprint | Ursa7
|  | Not DevOps | Yes
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 1
|  | New | 1
|  | Cancelled | 1
Unkown
|  | (blank) | 10
|  | Grand Total | 16
|  | Grand Total | 16
|  | Chart Total | Sprint 7 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()} |  |  | Total P0/P1 Bugs: ${bpHelper.getTotalP0P1BugCount()}
Custom P0/P1 Bugs: ${bpHelper.getCustomP0P1BugCount()}
| Release | Ursa
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Ursa
| Type | Bug
| Team Grouped | (All)
| Status | Bug: Closed
| Row Labels | Count of Key
| U1 | 1
U2
U3
| U4 | 1
U5
U6
U7
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Ursa Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | DevOps Type | Not DevOps | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-ursa-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(AE2, "rsa", ""), "itan", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getUrsaComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.getDevOpsType(issue)} | $[IF(K2="DevOps","","Yes")] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | RD | Epic: New | [16 empty] | RD | [8 empty] | Ursa1 |  | Ursa |  | New | Process Improvements |  | RD | RD | [6 empty] | Yes
key | Story |  | RD | Epic: Decomposition | [8 empty] | 5 | [7 empty] | RD | [8 empty] | Ursa2 |  |  |  | Ready | Version Compare |  | RD | RD | [6 empty] | Yes | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | RD | Epic: Review | [8 empty] | 10 | [7 empty] | RD | [8 empty] | Ursa3 |  |  |  | In Dev | Traces |  | RD | RD | [6 empty] | Yes | Yes
key | Tech Debt |  | RD | Epic: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Ursa4 |  |  |  | Validation | DevOps |  | RD | RD | [7 empty] | Yes
key | Bug |  | RD | Epic: In Development | [16 empty] | RD | [8 empty] | Ursa5 |  |  |  | Closed | R&D Bucket |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Ursa6 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Cancelled | [16 empty] | RD | [8 empty] | Ursa7 |  |  |  | Unkown |  |  | RD | RD | [6 empty] | Yes | No
key | DevOps |  | RD | Epic: Demo | [16 empty] | RD | [8 empty] | Ursa2 | [6 empty] | RD | RD | [6 empty] | Yes
key | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Ursa3 | U1 | [5 empty] | DevOps | DevOps | [6 empty] | Yes
key |  |  | RD | Story: Review | [16 empty] | RD | [8 empty] | Ursa4 | U2 | [13 empty] | Yes
key | Story |  | RD | Story: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Ursa5 | U3 | [13 empty] | Yes | Yes
key |  |  | RD | Story: In Development | [16 empty] | RD | [8 empty] | Ursa6 | U4 | [13 empty] | Yes
key | DevOps |  |  | Story: Validation | [8 empty] | 10 | [16 empty] | Ursa1 | U5 | [12 empty] | Development/Internal Support | Yes
key | DevOps |  |  | Story: Demo Checkpoint | [8 empty] | 10 | [16 empty] | Ursa7 | U6 | [12 empty] | Production Support | Yes
key | DevOps |  |  | Story: Done | [8 empty] | 10 | [16 empty] | Ursa3 | U1 | [12 empty] | Planned - Deployment and Release | Yes
key | DevOps |  |  | Story: In Development - On Hold | [8 empty] | 10 | [16 empty] | Ursa4 | U2 | [12 empty] | Planned - Operational Efficiency | Yes
key | DevOps |  |  | Story: Demo Checkpoint - On Hold | [8 empty] | 10 | [16 empty] | Ursa5 | U3 | [12 empty] | Planned - Platform Health | Yes
key | DevOps |  |  | Story: Prototype Done | [8 empty] | 10 | [16 empty] | Ursa6 | U4 | [12 empty] | Planned - Security | Yes
key | DevOps |  |  | Story: Ready for Validation | [8 empty] | 10 | [16 empty] | Ursa1 | U5 | [12 empty] | Time Off / Conferences | Yes
key |  |  |  | Story: Validation - On Hold | [25 empty] | Ursa2 | U6 | [13 empty] | Yes
key |  |  |  | Story: Cancelled | [25 empty] | Ursa7 | U1 | [13 empty] | Yes
key |  |  |  | Tech Debt: New | [25 empty] | Ursa4 | U1 | [13 empty] | Yes
key |  |  |  | Tech Debt: Review | [40 empty] | Yes
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30 | [31 empty] | Yes
key |  |  |  | Tech Debt: In Development | [27 empty] | Titan | [12 empty] | Yes
key |  |  |  | Tech Debt: Validation | [40 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | New | [10 empty] | Yes
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | Ready | [10 empty] | Yes
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | In Dev | [10 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | Validation | [10 empty] | Yes
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | Closed | [10 empty] | Yes
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | Cancelled | [10 empty] | Yes
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Ursa7 |  |  |  | Unkown | [10 empty] | Yes
key |  |  |  | Tech Debt: Cancelled | [25 empty] | Ursa1 | [14 empty] | Yes
key |  |  |  | Bug: New | [40 empty] | Yes
key |  |  |  | Bug: Triage | [40 empty] | Yes
key | Bug |  |  | Bug: Ready | [26 empty] | U1 | Ursa | Highest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development | [26 empty] | U2 | Ursa | High |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Validation | [26 empty] | U3 | Ursa | Medium |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | U4 | Ursa | Low |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: New - On Hold | [26 empty] | U5 | Ursa | Lowest |  |  |  | RD | [7 empty] | Yes
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | U6 | Ursa | Low |  |  |  | RD | [7 empty] | Yes
key | bug |  |  | Bug: Validation - On Hold | [26 empty] | U7 | Ursa | [12 empty] | Yes
key |  |  |  | Bug: Investigate | [40 empty] | Yes
key | [44 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | U1 | Ursa | Highest |  |  |  | RD | [7 empty] | Yes
key | Epic | [8 empty] | Version Compare |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Ursa |  |  | DevOps |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic | [8 empty] | Traces |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Ursa |  |  | Version Compare |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic |  |  | Story: New | [5 empty] | Process Artifact |  |  | 10 |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Ursa |  | New | Process Improvements |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key | Story |  |  | Story: Ready | [5 empty] | Process Artifact |  |  | 10 |  | 200 | 150 | [15 empty] | Ursa |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [5 empty] | Process Artifact |  |  | 10 |  | 200 | 150 | [15 empty] | Ursa |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Ursa |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Ursa |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Ursa |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Ursa |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Ursa |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Ursa |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Ursa |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Ursa |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Ursa |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Ursa |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Ursa |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Ursa |  | Closed |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Ursa |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Ursa |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Ursa |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Ursa |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Ursa |  | Closed |  |  | RD | [7 empty] | Yes
key | [44 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Ursa |  |  | Process Improvements | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Ursa |  |  | Version Compare | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Ursa |  |  | R&D Bucket | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Ursa |  |  | Other | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Ursa |  |  | Traces | [9 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200 | [15 empty] | U1 | Ursa |  |  | DevOps |  | NW
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200.125 | [15 empty] | U2 | Ursa |  |  | CI/CD |  | ngStars | [7 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200 | [15 empty] | U3 | Ursa |  |  | Version Compare |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U4 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U5 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U6 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U1 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U2 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U3 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U4 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U5 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U6 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U1 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U2 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | U1 | [13 empty] | Yes
key | DevOps |  |  | DevOps: New | [40 empty] | Yes
key | DevOps |  |  | DevOps: Review | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint | [40 empty] | Yes
key | DevOps |  |  | DevOps: Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Prototype Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready for Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Cancelled | [40 empty] | Yes | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).