## Release
0
70

## Admin
0

## BP Integration
0

## AA Integration
0
0

## MS PA Integration
#REF!

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [7 empty] | Release, Admin, Blue Prism Integration | Automation Anywhere Integration | Release | Admin | Blue Prism Integration | Automation Anywhere Integration | Release |  | Admin |  | Blue Prism Integration |  | Automation Anywhere Integration |  |  | Release | X-Ray |  | MS Power Automate Integration
Actual | 441.4% | Start Date | End Date |  | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic |  | Ideal Progress | Actual Progress | Ideal Burndown | Actual Burndown
Remainder | 0% | 2020-06-03 | 2020-08-25 | [5 empty] | 0% | 0% | 12% | 11% | 71% | 3% | 420 | 287 | 50 | 82 | 50 | 10 | 80 | 95 | 2020-07-01 | Not DevOps | Yes |  | 0% | 0% | 100 | 100
|  |  | 2020-08-25 |  | X1 | 2020-06-03 | 2020-06-16 | 10 | 17.24% | 17.24% | 30% | 58% | 100% | 16% | 347.5862 | 361 | 41.3793 | 47 | 41.3793 | 0 | 66.2069 | 79 | 2020-08-03 |  |  |  | 17.24% | 17% | 82.7586 | 83
Release |  | Report Date ??? | ${bpHelper.getToday()} |  | X2 | 2020-06-17 | 2020-06-30 | 10 | 34.48% | 34.48% | 50% | 89% | 97% | 34% | 275.1724 | 220.5 | 32.7586 | 10.5 | 32.7586 | 1 | 52.4138 | 68 | 2020-09-07 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate | 34.48% | 53% | 65.5172 | 21
Actual | #DIV/0! | Report Date | 2021-06-01 |  | X3 | 2020-07-01 | 2020-07-14 | 9 | 50% | 50% | 63% | 87% | 100% | 79% | 210 | 173.3 | 25 | 14 | 25 | 0 | 40 | 22 | 2020-10-12 | (blank) |  |  | 50% | 88% | 50 | 5
Remainder | #DIV/0! |  |  |  | X4 | 2020-07-15 | 2020-07-28 | 10 | 67.24% | 67.24% | 75% | 97% | 79% | 100% | 137.5862 | 124 | 16.3793 | 3.5 | 16.3793 | 10 | 26.2069 | 0 |  | Grand Total |  |  | 67.24% | 100% | 32.7586 | 0
[5 empty] | X5 | 2020-07-29 | 2020-08-11 | 9 | 82.76% | 82.76% | 89% | 98% | 100% | 100% | 72.4138 | 51.5 | 8.6207 | 2 | 8.6207 | 0 | 13.7931 | 0 |  |  |  |  | 82.76% | 100% | 17.2414 | 0
Admin |  |  |  |  | X6 | 2020-08-12 | 2020-08-25 | 10 | 100% | 100% | #DIV/0! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | #REF! | 0 | #REF! |  |  |  |  | 100% | #REF! | 0 | #REF!
Actual | #REF!
Remainder | #REF!
Blue Prism Integration
Actual | #REF!
Remainder | #REF!
Time Elapsed
Automation Anywhere Integration | [26 empty] | Actual | 441.4%
Actual | #REF! | [25 empty] | Remainder | 0%
Remainder | #REF!
MS Power Automate Integration
Time Elapsed Automation Anywhere Integration | [26 empty] | Actual | #REF!
Actual | 441.4% | [25 empty] | Remainder | #REF!
Remainder | 0%
|  | Release | X-Ray |  | Release | X-Ray |  | Release | X-Ray |  | Release | X-Ray |  | Feature | Cost
Release | X-Ray | Type | Epic |  | Type | Epic |  | Type | Epic |  | Type | Epic |  | Release | 420
Type | Epic | ST:Components | Admin |  | ST:Components | BluePrism Integration |  | ST:Components | Automation Anywhere Integration |  | ST:Components | Microsoft Power Automate Integration |  | Admin | 50
Not DevOps | Yes | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  | Blue Prism Integration | 50
[14 empty] | Automation Anywhere Integration | 80
Values |  | Values |  |  | Values |  |  | Values |  |  | Values |  |  | MS Power Automate Integration | 100
Done | 0 | Done | 0 |  | Done | 0 |  | Done | 0 |  | Done | 0
In Validation |  | In Validation |  |  | In Validation |  |  | In Validation |  |  | In Validation
In Dev |  | In Dev |  |  | In Dev |  |  | In Dev |  |  | In Dev
Ready |  | Ready |  |  | Ready |  |  | Ready |  |  | Ready
Not Decomposed | 0 | Not Decomposed | 0 |  | Not Decomposed | 0 |  | Not Decomposed | 0 |  | Not Decomposed | 0
Release | X-Ray
Type | Epic | Release | X-Ray |  | Release | X-Ray |  | Release | X-Ray |  | Release | X-Ray
Not DevOps | Yes | Type | Epic |  | Type | Epic |  | Type | Epic |  | Type | Epic
|  | ST:Components | Admin |  | ST:Components | BluePrism Integration |  | ST:Components | Automation Anywhere Integration |  | ST:Components | Microsoft Power Automate Integration
Sum of Epic Total Estimate
| 0 | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate
|  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Type | DevOps
Type | Epic
Release | X-Ray |  | Row Labels | Sum of Story Points
Not DevOps | Yes |  | Development/Internal Support | 10
|  |  | Planned - Deployment and Release | 10
Row Labels | Sum of Epic Total Estimate |  | Planned - Operational Efficiency | 10
Blue Prism Integration |  |  | Planned - Platform Health | 10
Grand Total |  |  | Planned - Security | 10
|  |  | Production Support | 10
|  |  | Time Off / Conferences | 10
(blank)
|  |  | Grand Total | 70
| 0 |  |  | 70

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | Admin | [7 empty] | Blue Prism Integration | [7 empty] | Automation Anywhere Integration | [12 empty] | MS Power Automate Integration
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | [5 empty] | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
|  |  | 324.6 | 420 | 226.6 | 198.6 | 37.6 | 287 | 61.18% | 11.58% | 92 | 50 | 87 | 87 | 10 | 82 | 94.57% | 10.87% | 34.6 | 50 | 34.6 | 34.6 | 24.6 | 10 | 100% | 71.1% | 98 | 80 | 89 | 61 | 3 | 95 | 62.24% | 3.061% | [5 empty] | 100 | 100 | 16 | 16 | 0 | 100 | 16% | 0%
X1 | 2020-06-03 | 2020-06-16 | 515.6 | 420 | 424.1 | 401.1 | 154.6 | 361 | 77.79% | 29.98% | 112 | 50 | 97.5 | 97.5 | 65 | 47 | 87.05% | 58.04% | 36.6 | 50 | 36.6 | 36.6 | 36.6 | 0 | 100% | 100% | 94 | 80 | 94 | 92 | 15 | 79 | 97.87% | 15.96% | [5 empty] | 100 | 100 | 23 | 23 | 17 | 83 | 23% | 17%
X2 | 2020-06-17 | 2020-06-30 | 444.6 | 420 | 444.6 | 413.6 | 224.1 | 220.5 | 93.03% | 50.4% | 97.5 | 50 | 97.5 | 97.5 | 87 | 10.5 | 100% | 89.23% | 37.6 | 50 | 37.6 | 37.6 | 36.6 | 1 | 100% | 97.34% | 102.5 | 80 | 102.5 | 102.5 | 34.5 | 68 | 100% | 33.66% | [5 empty] | 45 | 100 | 45 | 39 | 24 | 21 | 86.67% | 53.33%
X3 | 2020-07-01 | 2020-07-14 | 472.9 | 420 | 472.9 | 447.4 | 299.6 | 173.3 | 94.61% | 63.35% | 109.5 | 50 | 109.5 | 109 | 95.5 | 14 | 99.54% | 87.21% | 37.6 | 50 | 37.6 | 37.6 | 37.6 | 0 | 100% | 100% | 106.5 | 80 | 106.6 | 106.5 | 84.5 | 22 | 100% | 79.34% | [5 empty] | 41 | 100 | 41 | 41 | 36 | 5 | 100% | 87.8%
X4 | 2020-07-15 | 2020-07-28 | 500.9 | 420 | 509 | 489.9 | 376.9 | 124 | 97.8% | 75.24% | 113.5 | 50 | 113.5 | 113.5 | 110 | 3.5 | 100% | 96.92% | 47.6 | 50 | 47.6 | 47.6 | 47.6 | 0 | 100% | 100% | 106.5 | 80 | 106.5 | 106.5 | 106.5 | 0 | 100% | 100% | Release | X-Ray |  |  |  | 42.5 | 100 | 42.5 | 42.5 | 37.5 | 5 | 100% | 88.24%
X5 | 2020-07-29 | 2020-08-11 | 452.9 | 420 | 452.9 | 452.9 | 401.4 | 51.5 | 100% | 88.63% | 96.5 | 50 | 96.5 | 96.5 | 94.5 | 2 | 100% | 97.93% | 47.6 | 50 | 47.6 | 47.6 | 47.6 | 0 | 100% | 100% | 106.5 | 80 | 106.5 | 106.5 | 106.5 | 0 | 100% | 100% | Not DevOps | Yes |  |  |  | 42.5 | 100 | 42.5 | 42.5 | 42.5 | 0 | 100% | 100%
X6 | 2020-08-12 | 2020-08-25 | 0 | 420 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #REF! | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 80 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Column Labels
Epic
[35 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
(blank)
Grand Total

## _ReadinessData (hidden)
Not DevOps | Yes
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate |  | Not DevOps | Yes
Epic | 140
Grand Total | 140 |  | Row Labels | Sum of Story Points
|  |  | (blank) | 0
|  |  | RD | 15
|  |  | Grand Total | 15
Sprint | Epics New | Stories Ready
X1 | 114.5 | 157.5
X2 | 31 | 86
X3 | 89.5 | 107
X4 | 128 | 144
X5 | 122 | 145.5
X6 | 140 | 15

## Team Backlog
0

## _TeamBacklogData (hidden)
Release | X-Ray
Type | (Multiple Items)
Team Grouped | (All)
Not DevOps | Yes
Row Labels | Sum of Story Points
Grand Total
Grand Total | 0

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Not DevOps | Yes
Row Labels | Sum of Story Points | Historical
X1 |  | Sprint | R&D | Total
X2 |  | X1 | 118
X3 |  | X2 | 71.5
X4 |  | X3 | 85.5
X5 |  | X4 | 96.25
X6 |  | X5 | 57
Grand Total |  | X6
|  | Total | 428.25 | 0

## Active Sprint
20

## _ActiveSprintData
Active Sprint | Austin3 | Type | (Multiple Items)
|  | Last Sprint | Austin3
|  | Not DevOps | Yes
|  | Row Labels | Sum of Story Points
|  | In Dev | 10
|  | (blank) | 10
|  | Grand Total | 20
|  | Grand Total | 20
|  | Chart Total | Sprint Austin3 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()} |  |  | Total P0/P1 Bugs: ${bpHelper.getTotalP0P1BugCount()}
Custom P0/P1 Bugs: ${bpHelper.getCustomP0P1BugCount()}
| Release | Austin
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Austin
| Sprint Label | A3
| Type | Bug
| Status | Bug: Closed
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5

## Issues
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Release Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | DevOps Type | Not DevOps | Backlog Health | Active in Release # | Quality Score | Story Decomposed | Story Decomposed SP | Story Remaining SP | Release Component New | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-canada-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(AE2, "elarus", ""), "ustin", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getReleaseComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.getDevOpsType(issue)} | $[IF(K2="DevOps","","Yes")] | ${bpHelper.isInBacklogHealth(issue)} | ${fieldHelper.getFieldValueByName(issue, "Active in Release #")} | ${fieldHelper.getFieldValueByName(issue, "Quality Score")} | ${bpHelper.isStoryDecopmosed(issue)} | $[IF(AX2="Yes", N2, IF(AX2="No",0,""))] | $[IF(E2="Story: Done",0,IF(OR(B2="Story",B2="Spike"), N2, ""))] | ${bpHelper.getReleaseComponent(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key 4 | Epic |  | RD | Epic: New | [16 empty] | RD | [8 empty] | Austin1 |  | X-Ray |  | New | Blue Prism Integration |  | RD | RD | [6 empty] | Yes |  | 11.3
key 5 | Story |  | RD | Epic: Decomposition | [5 empty] | Admin |  |  | 5 | [7 empty] | RD | [8 empty] | Austin2 |  | Astin |  | Ready | Admin |  | RD | RD | [6 empty] | Yes | Yes | 12 |  | Yes |  |  | AA Migration Demo PoC
key 6 | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | RD | Epic: Review | [8 empty] | 10 | [7 empty] | RD | [8 empty] | Austin3 |  |  |  | In Dev | Automation Anywhere Integration |  | RD | RD | [6 empty] | Yes | Yes |  |  | No |  |  | Digital Blueprint Licensing
key 7 | Tech Debt |  | RD | Epic: Ready | [8 empty] | 20 | [7 empty] | RD | [8 empty] | Austin4 |  |  |  | Validation | DevOps |  | RD | RD | [7 empty] | Yes | [5 empty] | New Impact Analysis
key 8 | Bug |  | RD | Epic: In Development | [16 empty] | RD | [8 empty] | Austin5 |  |  |  | Closed | R&D Bucket |  | RD | RD | [6 empty] | Yes | No | [5 empty] | Import/Export Projects MVP
key 9 | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Austin5 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [6 empty] | Yes | No | [5 empty] | AD and FA Settings
key 10 | DevOps |  | RD | Epic: Cancelled | [16 empty] | RD | [8 empty] | Austin1 |  |  |  | Unkown |  |  | RD | RD | [6 empty] | Yes | No | [5 empty] | Convert Custom Properties to Standard
key 11 | DevOps |  | RD | Epic: Demo | [16 empty] | RD | [8 empty] | Austin2 | [6 empty] | RD | RD | [6 empty] | Yes | [6 empty] | Pre-Loaded Instance Configuration
key 12 | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Austin3 | A1 | [5 empty] | DevOps | DevOps | [6 empty] | Yes | [6 empty] | Dropping SQL Server 2012
key 13 |  |  | RD | Story: Review | [16 empty] | RD | [8 empty] | Austin4 | A2 | [13 empty] | Yes |  | 11.4 |  |  |  |  | R&D Bucket
key 14 | Story |  | RD | Story: Ready | [5 empty] | Admn |  |  | 0 | [7 empty] | RD | [8 empty] | Austin5 | A3 | Austin | [12 empty] | Yes | Yes | 12 |  |  |  |  | Other
key 15 |  |  | RD | Story: In Development | [16 empty] | RD | [8 empty] | Austin6 | A4 | [13 empty] | Yes
key 16 | DevOps |  |  | Story: Validation | [8 empty] | 10 | [16 empty] | Austin1 | A5 | [12 empty] | Development/Internal Support | Yes
key 17 | DevOps |  |  | Story: Demo Checkpoint | [8 empty] | 10 | [16 empty] | Austin6 | A6 | [12 empty] | Production Support | Yes
key 18 | DevOps |  |  | Story: Done | [8 empty] | 10 | [16 empty] | Austin3 | A1 | [12 empty] | Planned - Deployment and Release | Yes
key 19 | DevOps |  |  | Story: In Development - On Hold | [8 empty] | 10 | [16 empty] | Austin4 | A2 | [12 empty] | Planned - Operational Efficiency | Yes
key 20 | DevOps |  |  | Story: Demo Checkpoint - On Hold | [8 empty] | 10 | [16 empty] | Austin5 | A3 | [12 empty] | Planned - Platform Health | Yes
key 21 | DevOps |  |  | Story: Prototype Done | [8 empty] | 10 | [16 empty] | Austin5 | A4 | [12 empty] | Planned - Security | Yes
key 22 | DevOps |  |  | Story: Ready for Validation | [8 empty] | 10 | [16 empty] | Austin1 | A5 | [12 empty] | Time Off / Conferences | Yes
key 23 |  |  |  | Story: Validation - On Hold | [25 empty] | Austin6 | A6 | [13 empty] | Yes
key 24 |  |  |  | Story: Cancelled | [25 empty] | Austin5 | A5 | [13 empty] | Yes
key 25 |  |  |  | Tech Debt: New | [25 empty] | Austin5 | A5 | [13 empty] | Yes
key 26 |  |  |  | Tech Debt: Review | [40 empty] | Yes
key 27 | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30 | [31 empty] | Yes
key 28 |  |  |  | Tech Debt: In Development | [27 empty] | X-Ray | [12 empty] | Yes
key 29 |  |  |  | Tech Debt: Validation | [40 empty] | Yes
key 30 | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | New | [10 empty] | Yes
key 31 | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | Ready | [10 empty] | Yes
key 32 | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | In Dev | [10 empty] | Yes
key 33 | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | Validation | [10 empty] | Yes
key 34 | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | Closed | [10 empty] | Yes
key 35 | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | Cancelled | [10 empty] | Yes
key 36 |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Austin6 |  |  |  | Unkown | [10 empty] | Yes
key 37 |  |  |  | Tech Debt: Cancelled | [25 empty] | Austin6 | [14 empty] | Yes
key 38 |  |  |  | Bug: New | [40 empty] | Yes
key 39 |  |  |  | Bug: Triage | [40 empty] | Yes
key 40 | Bug |  |  | Bug: Ready | [26 empty] | A1 | Austin | Highest |  |  |  | RD | [7 empty] | Yes |  | 12
key 41 | Bug |  |  | Bug: In Development | [26 empty] | A2 | Austin | High |  |  |  | RD | [7 empty] | Yes |  | 12
key 42 | Bug |  |  | Bug: Validation | [26 empty] | A3 | Austin | Medium |  |  |  | RD | [7 empty] | Yes |  | 12
key 43 | Bug |  |  | Bug: Closed | [26 empty] | A4 | Austin | Low |  |  |  | RD | [7 empty] | Yes |  | 12
key 44 | Bug |  |  | Bug: New - On Hold | [26 empty] | A5 | Austin | Lowest |  |  |  | RD | [7 empty] | Yes |  | 12
key 45 | Bug |  |  | Bug: In Development - On Hold | [26 empty] | A1 | Austin | Low |  |  |  | RD | [7 empty] | Yes |  | 12
key 46 | bug |  |  | Bug: Validation - On Hold | [26 empty] | A1 | Austin | [12 empty] | Yes
key 47 |  |  |  | Bug: Investigate | [40 empty] | Yes
key 48 | [44 empty] | Yes
key 49 | Bug |  |  | Bug: Closed | [26 empty] | A1 | Austin | Highest |  |  |  | RD | [7 empty] | Yes
key 50 | Epic | [8 empty] | Microsoft Power Automate Integration |  |  |  |  | 100 | 150 | [5 empty] | 180 | [9 empty] | Austin |  |  | MS Power Automate Integration |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key 51 | Epic | [8 empty] | BluePrism Integration |  |  |  |  | 50 | 150 | [5 empty] | 180 | [9 empty] | Austin |  |  | Admin |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key 52 | Epic |  |  | Story: New | [5 empty] | Automation Anywhere Integration |  |  | 10 |  | 50 | 150 | [5 empty] | 180 | [9 empty] | Austin |  | New | Automation Anywhere Integration |  | RD |  | 30 | 60 | 40 |  |  |  | Yes
key 53 | Story |  |  | Story: Ready | [5 empty] | Automation Anywhere Integration |  |  | 10 |  | 50 | 150 | [15 empty] | Austin |  | Ready |  |  | RD | [7 empty] | Yes
key 54 | Story |  |  | Story: In Development | [5 empty] | Automation Anywhere Integration |  |  | 10 |  | 750 | 150 | [15 empty] | Austin |  | In Dev |  |  | RD | [7 empty] | Yes
key 55 | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Austin |  | Validation |  |  | RD | [7 empty] | Yes
key 56 | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Austin |  | Closed |  |  | RD | [7 empty] | Yes
key 57 | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Austin |  | New |  |  | RD | [7 empty] | Yes
key 58 | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Austin |  | Ready |  |  | RD | [7 empty] | Yes
key 59 | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Austin |  | In Dev |  |  | RD | [7 empty] | Yes
key 60 | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Austin |  | Validation |  |  | RD | [7 empty] | Yes
key 61 | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Austin |  | Closed |  |  | RD | [7 empty] | Yes
key 62 | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Austin |  | New |  |  | RD | [7 empty] | Yes
key 63 | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Austin |  | Ready |  |  | RD | [7 empty] | Yes
key 64 | Story |  |  | Story: In Development | [8 empty] | 30 | [16 empty] | Austin5 | A1 | Austin |  | In Dev |  |  | RD | [7 empty] | Yes
key 65 | Story |  |  | Story: Validation | [8 empty] | 30 | [16 empty] | Austin5 | A1 | Austin |  | Validation |  |  | RD | [7 empty] | Yes
key 66 | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Austin |  | Closed |  |  | RD | [7 empty] | Yes
key 67 | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Austin |  | New |  |  | RD | [7 empty] | Yes
key 68 | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Austin |  | Ready |  |  | RD | [7 empty] | Yes
key 69 | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Austin |  | In Dev |  |  | RD | [7 empty] | Yes
key 70 | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Austin |  | Validation |  |  | RD | [7 empty] | Yes
key 71 | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Austin |  | Closed |  |  | RD | [7 empty] | Yes
key 72 | [31 empty] | Austin | [12 empty] | Yes
key 73 | Epic | [8 empty] | Admin |  |  |  |  | 100 | [16 empty] | Austin |  |  | Automation Anywhere Integration | [9 empty] | Yes
key 74 | Epic | [13 empty] | 50 | [16 empty] | Austin |  |  | Admin | [9 empty] | Yes
key 75 | Epic | [13 empty] | 50 | [16 empty] | Austin |  |  | R&D Bucket | [9 empty] | Yes
key 76 | Epic | [13 empty] | 50 | [16 empty] | Austin |  |  | Other | [9 empty] | Yes
key 77 | Epic | [13 empty] | 50 | [16 empty] | Austin |  |  | Blue Prism Integration | [9 empty] | Yes
key 78 | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | A1 | Austin |  |  | Admin |  | NW
key 79 | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | A2 | Austin |  |  | Blue Prism Integration |  | ngStars | [7 empty] | Yes
key 80 | Epic |  |  | Story: Done | [8 empty] | 30 |  | 50 | [15 empty] | A3 | Austin |  |  | Admin |  | Alpha | [7 empty] | Yes
key 81 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A4 | [5 empty] | Titan | [7 empty] | Yes
key 82 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A5 | [5 empty] | RD | [7 empty] | Yes
key 83 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A5 | [5 empty] | NW | [7 empty] | Yes
key 84 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A1 | [5 empty] | ngStars | [7 empty] | Yes
key 85 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A2 | [5 empty] | Alpha | [7 empty] | Yes
key 86 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A3 | [5 empty] | Titan | [7 empty] | Yes
key 87 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A4 | [5 empty] | RD | [7 empty] | Yes
key 88 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A5 | [5 empty] | NW | [7 empty] | Yes
key 89 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A1 | [5 empty] | ngStars | [7 empty] | Yes
key 90 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A1 | [5 empty] | Alpha | [7 empty] | Yes
key 91 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A2 | [5 empty] | Titan | [7 empty] | Yes
key 92 | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | A1 | [13 empty] | Yes
key 93 | DevOps |  |  | DevOps: New | [40 empty] | Yes
key 94 | DevOps |  |  | DevOps: Review | [40 empty] | Yes
key 95 | DevOps |  |  | DevOps: Ready | [40 empty] | Yes
key 96 | DevOps |  |  | DevOps: In Development | [40 empty] | Yes
key 97 | DevOps |  |  | DevOps: Validation | [40 empty] | Yes
key 98 | DevOps |  |  | DevOps: Demo Checkpoint | [40 empty] | Yes
key 99 | DevOps |  |  | DevOps: Done | [40 empty] | Yes
key 100 | DevOps |  |  | DevOps: In Development - On Hold | [40 empty] | Yes
key 101 | DevOps |  |  | DevOps: Demo Checkpoint - On Hold | [40 empty] | Yes
key 102 | DevOps |  |  | DevOps: Prototype Done | [40 empty] | Yes
key 103 | DevOps |  |  | DevOps: Ready for Validation | [40 empty] | Yes
key 104 | DevOps |  |  | DevOps: Validation - On Hold | [40 empty] | Yes
key 105 | Bug |  |  | Bug: Closed | [25 empty] | Austin3 | A3 | Austin | Highest |  |  |  | RD | [7 empty] | Yes |  | 11.4
key 106 | Bug |  |  | Bug: Closed | [25 empty] | Austin3 | A3 | Austin | High |  |  |  | RD | [7 empty] | Yes |  | 11.4
key 107 | Bug |  |  | Bug: Closed | [25 empty] | Austin3 | A3 | Austin | Medium |  |  |  | RD | [7 empty] | Yes |  | 11.4
key 108 | Bug |  |  | Bug: Closed | [25 empty] | Austin3 | A3 | Austin | Low |  |  |  | RD | [7 empty] | Yes |  | 11.4
key 109 | Bug |  |  | Bug: Closed | [25 empty] | Austin3 | A3 | Austin | Lowest |  |  |  | RD | [7 empty] | Yes |  | 11.4
key 110 | DevOps |  |  | DevOps: Cancelled | [9 empty] | 90 | 100 | 50 | [5 empty] | 80 | [22 empty] | Yes |  | 11.4
key 111 | Epic | ??Admin | [7 empty] | Admin |  |  |  | 190 | 200 | 50 | [5 empty] | 180 | [9 empty] | Austin | [12 empty] | Yes |  | 11.4
key 112 | Epic | ??Admin - Active Directory & Federated Authentication Settings | [7 empty] | Admin - Active Directory & Federated Authentication Settings |  |  |  | 290 | 300 | 50 | [5 empty] | 280 | [9 empty] | Austin | [12 empty] | Yes |  | 11.4
key 113 | Epic | ??Impact Analysis | [7 empty] | Impact Analysis |  |  |  | 390 | 400 | 50 | [5 empty] | 380 | [9 empty] | Austin | [12 empty] | Yes |  | 11.4
key 114 | Epic | ??Installer | [7 empty] | Installer |  |  |  | 490 | 500 | 50 | [5 empty] | 480 | [9 empty] | Austin | [12 empty] | Yes |  | 11.4
key 115 | Epic | ??Tech Improvements | [7 empty] | Tech Improvements | [21 empty] | Austin | [12 empty] | Yes |  | 11.4 |  |  |  |  | </jt:forEach>

## Sheet (Epic)
Dev Sprint | Start Date | End Date | Progress | Total | Epic Decompsed | Story Decomposed | Completed | Remaining
A1 | 2020-08-26 | 2020-09-08 | [6 empty] | Release | (All)
A2 | 2020-09-09 | 2020-09-22 | 0% | 0 | 0 | 0 | 0 | 0 | Type | Epic
A3 | 2020-09-23 | 2020-10-06 | 83.33% | 300 | 190 | 180 | 250 | 50 | Not DevOps | Yes
A4 | 2020-10-07 | 2020-10-20
A5 | 2020-10-21 | 2020-11-03 | [6 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
A6 | 2020-11-04 | 2020-11-17 | [6 empty] | Admin | 300 | 190 | 180 | 50
[9 empty] | (blank) | 100
[9 empty] | ??Admin | 200 | 190 | 180 | 50
[9 empty] | Grand Total | 300 | 190 | 180 | 50
Formulas:
End Date = [Start Date]+13
End Date = [End Date, row above]+14
Start Date = [End Date, row above]+1

## Sheet (Story)
Dev Sprint | Start Date | End Date | Progress | Total | Decomposed | Completed | Remaining | Release | (All)
A1 | 2020-08-26 | 2020-09-08 | [5 empty] | Active in Release # | 12
A2 | 2020-09-09 | 2020-09-22 | [5 empty] | Type | (Multiple Items)
A3 | 2020-09-23 | 2020-10-06 | 0% | 0 | 0 | 0 | 0 | Not DevOps | Yes
A4 | 2020-10-07 | 2020-10-20 | 100% | 5 | 0 | 5 | 0
A5 | 2020-10-21 | 2020-11-03 | [5 empty] | Row Labels | Sum of Story Points | Sum of Story Decomposed SP | Sum of Story Remaining SP
A6 | 2020-11-04 | 2020-11-17 | [5 empty] | Admin | 5 | 0 | 0
[8 empty] | (blank) | 5 | 0 | 0
[8 empty] | Epic: Decomposition | 5 | 0 | 0
[8 empty] | (blank) | 0 | 0 | 0
[8 empty] | (blank) | 0 | 0 | 0
[8 empty] | Story: Ready | 0 | 0 | 0
[8 empty] | Grand Total | 5 | 0 | 0
Formulas:
End Date = [Start Date]+13
End Date = [End Date, row above]+14
Start Date = [End Date, row above]+1

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* Change in AE:30-37 Last Sprint to the current sprint
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).