## Release
2000

## UME
200

## Artifact List v2
200

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [6 empty] | Release, UME | Artifact List v2 | Release | UME | Artifact List v2 | Release |  | UME |  | Artifact List v2 |  |  | Release | Quasar
Actual | 54.31% | Start Date | End Date | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 45.69% | 2018-04-11 | 2018-10-02 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 2350 | 2023 | 1400 | 918 | 675 | 575 | 2018-07-11
|  |  | 2018-09-11 | Q1 | 2018-04-11 | 2018-04-17 | 5 | 4.31% | 4.95% | 4.81% | 3.99% | 6.03% | 2248.7069 | 2324.5 | 1339.6552 | 1274 | 641.5842 | 654 | 2018-07-12 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Release |  | Report Date ??? | ${bpHelper.getToday()} | Q2 | 2018-04-18 | 2018-05-01 | 10 | 12.93% | 14.85% | 12.56% | 7.65% | 18.53% | 2046.1207 | 2399.3 | 1218.9655 | 1544.3 | 574.7525 | 525.5 | 2018-07-13 | (blank) | 800
Actual | 75% | Report Date | 2018-07-11 | Q3 | 2018-05-02 | 2018-05-15 | 10 | 21.55% | 24.75% | 22.91% | 14.3% | 30.58% | 1843.5345 | 1859.5 | 1098.2759 | 1267.5 | 507.9208 | 462 | 2018-07-16 | Artifact List | 200 | 150
Remainder | 25% |  |  | Q4 | 2018-05-16 | 2018-05-29 | 9 | 29.31% | 33.66% | 28.57% | 18.67% | 37.6% | 1661.2069 | 1741 | 989.6552 | 1161 | 447.7723 | 458 | 2018-07-17 | Diagram Editor | 200 | 150
|  |  |  | Q5 | 2018-05-30 | 2018-06-12 | 10 | 37.93% | 43.56% | 35.15% | 26.28% | 43.97% | 1458.6207 | 1597 | 868.9655 | 1032.5 | 380.9406 | 427.5 | 2018-05-21 | Grand Total | 1200 | 300
UME |  |  |  | Q6 | 2018-06-13 | 2018-06-26 | 10 | 46.55% | 53.47% | 47.52% | 37.55% | 57.92% | 1256.0345 | 1184.5 | 748.2759 | 743.5 | 314.1089 | 321.5 | 2018-07-02
Actual | 25% |  |  | Q7 | 2018-06-27 | 2018-07-10 | 9 | 54.31% | 62.38% | 55.8% | 45.86% | 67.89% | 1073.7069 | 1001 | 639.6552 | 634 | 253.9604 | 249.5 | 2018-08-06
Remainder | 75% |  |  | Q8 | 2018-07-11 | 2018-07-17 | 0 | 54.31% | 62.38% | 75% | 25% | 25% | 1073.7069 | 300 | 639.6552 | 150 | 253.9604 | 150 | 2018-09-03
|  |  |  | Q9 | 2018-07-18 | 2018-07-31 | 10 | 62.93% | 72.28% |  |  |  | 871.1207 |  | 518.9655 |  | 187.1287 |  | 2018-10-08
Artifact List v2 |  |  |  | Q10 | 2018-08-01 | 2018-08-14 | 9 | 70.69% | 81.19% |  |  |  | 688.7931 |  | 410.3448 |  | 126.9802
Actual | 25% |  |  | Q11 | 2018-08-15 | 2018-08-28 | 10 | 79.31% | 91.09% |  |  |  | 486.2069 |  | 289.6552 |  | 60.1485
Remainder | 75% |  |  | Q12 | 2018-08-29 | 2018-09-11 | 9 | 87.07% | 100% |  |  |  | 303.8793 |  | 181.0345 |  | 0
|  |  |  | Q13 | 2018-09-12 | 2018-09-25 | 10 | 95.69% |  |  |  |  | 101.2931 |  | 60.3448
Time Elapsed Artifact List v2 |  |  |  | Q14 | 2018-09-26 | 2018-10-02 | 5 | 100% |  |  |  |  | 0 |  | 0
Actual | 62.38%
Remainder | 37.62%
|  | Release | Quasar | Release | Quasar
Release | Quasar | Type | Epic | Type | Epic
Type | Epic | ST:Components | Diagram Editor | ST:Components | Artifact List
Values |  | Values |  | Values
Done | 900 | Done | 50 | Done | 50
In Validation | 80 | In Validation | 40 | In Validation | 40
In Dev | 120 | In Dev | 60 | In Dev | 60
Ready | 60 | Ready | 30 | Ready | 30
Not Decomposed | 840 | Not Decomposed | 20 | Not Decomposed | 20
Release | Quasar | Release | Quasar | Release | Quasar
Type | Epic | Type | Epic | Type | Epic
|  | ST:Components | Diagram Editor | ST:Components | Artifact List
Sum of Epic Total Estimate
1200 | 2000 | Sum of Epic Total Estimate |  | Sum of Epic Total Estimate
|  | 200 | 200 | 200 | 200
Type | Epic
Release | Quasar
Row Labels | Sum of Epic Total Estimate
UME | 200
Artifact List v2 | 200
R&D Bucket | 200
Other | 200
Grand Total | 800
Grand Total | 800

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | UME | [7 empty] | Artifact List v2
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
P8 |  |  | 2023 | 2350 | 938.5 | 411.5 | 0 | 2023 | 20.34% | 0% | 918 | 1400 | 141 | 83 | 0 | 918 | 9.041% | 0% | 575 | 675 | 350 | 215 | 0 | 575 | 37.39% | 0%
Q1 | 2018-04-04 | 2018-04-17 | 2442 | 2350 | 1008 | 569.5 | 117.5 | 2324.5 | 23.32% | 4.812% | 1327 | 1400 | 273 | 134 | 53 | 1274 | 10.1% | 3.994% | 696 | 675 | 389 | 261 | 42 | 654 | 37.5% | 6.034%
Q2 | 2018-04-18 | 2018-05-01 | 2743.8 | 2350 | 2218.3 | 811 | 344.5 | 2399.3 | 29.56% | 12.56% | 1672.3 | 1400 | 1213.3 | 268 | 128 | 1544.3 | 16.03% | 7.654% | 645 | 675 | 615 | 365 | 119.5 | 525.5 | 56.59% | 18.53%
Q3 | 2018-05-02 | 2018-05-15 | 2412 | 2350 | 2128.5 | 974 | 552.5 | 1859.5 | 40.38% | 22.91% | 1479 | 1400 | 1226.5 | 336.5 | 211.5 | 1267.5 | 22.75% | 14.3% | 665.5 | 675 | 635.5 | 464 | 203.5 | 462 | 69.72% | 30.58%
Q4 | 2018-05-16 | 2018-05-29 | 2437.5 | 2350 | 2265 | 1172.5 | 696.5 | 1741 | 48.1% | 28.57% | 1427.5 | 1400 | 1283 | 392 | 266.5 | 1161 | 27.46% | 18.67% | 734 | 675 | 707 | 597.5 | 276 | 458 | 81.4% | 37.6%
Q5 | 2018-05-30 | 2018-06-12 | 2462.5 | 2350 | 2354.5 | 1363.5 | 865.5 | 1597 | 55.37% | 35.15% | 1400.5 | 1400 | 1336.5 | 476.5 | 368 | 1032.5 | 34.02% | 26.28% | 763 | 675 | 726 | 675 | 335.5 | 427.5 | 88.47% | 43.97% | Release | (All)
Q6 | 2018-06-13 | 2018-06-26 | 2257 | 2350 | 2157.5 | 1478 | 1072.5 | 1184.5 | 65.49% | 47.52% | 1190.5 | 1400 | 1130 | 558.5 | 447 | 743.5 | 46.91% | 37.55% | 764 | 675 | 733 | 682 | 442.5 | 321.5 | 89.27% | 57.92%
Q7 | 2018-06-27 | 2018-07-10 | 2264.5 | 2350 | 2177 | 1563.5 | 1263.5 | 1001 | 69.04% | 55.8% | 1171 | 1400 | 1113.5 | 614 | 537 | 634 | 52.43% | 45.86% | 777 | 675 | 755 | 704 | 527.5 | 249.5 | 90.6% | 67.89% |  | Column Labels
Q8 | 2018-07-11 | 2018-07-17 | 1200 | 2350 | 0 | 360 | 900 | 300 | 30% | 75% | 200 | 1400 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 675 | 0 | 180 | 50 | 150 | 90% | 25% |  | Epic
Q9 | 2018-07-18 | 2018-07-31 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675 | [6 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
Q10 | 2018-08-01 | 2018-08-14 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675 | [6 empty] | Artifact List | 200 |  | 180 | 150
Q11 | 2018-08-15 | 2018-08-28 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675 | [6 empty] | Diagram Editor | 200 |  | 180 | 150
Q12 | 2018-08-29 | 2018-09-11 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675 | [6 empty] | (blank) | 800
Q13 | 2018-09-12 | 2018-09-25 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675 | [6 empty] | Grand Total | 1200 |  | 360 | 300
Q14 | 2018-09-26 | 2018-10-09 |  | 2350 | [7 empty] | 1400 | [7 empty] | 675

## _ReadinessData (hidden)
Row Labels | Sum of Epic Not Decomposed Estimate
Epic | 840
Grand Total | 840
Type | (Multiple Items)
Status | (Multiple Items)
Sum of Story Points
150
Sprint | Epics New | Stories Ready
Q1 | 1872.5 | 227.5
Q2 | 1932.75 | 291
Q3 | 1438 | 286
Q4 | 1265 | 339.5
Q5 | 1099 | 348
Q6 | 779 | 348
Q7 | 701 | 217
Q8 | 840 | 150
Q9
Q10
Q11
Q12
Q13
Q14

## Team Backlog
50
100
150
200

## _TeamBacklogData (hidden)
Release | Quasar | Release | Quasar | Release | Quasar | Release | Quasar
Type | (Multiple Items) | Type | (Multiple Items) | Type | (Multiple Items) | Type | (Multiple Items)
Team Grouped | Alpha | Team Grouped | ngStars | Team Grouped | NW | Team Grouped | SoftTeco
Row Labels | Sum of Story Points | Row Labels | Sum of Story Points | Row Labels | Sum of Story Points | Row Labels | Sum of Story Points
Closed | 10 | Closed | 20 | Closed | 30 | Closed | 40
Validation | 10 | Validation | 20 | Validation | 30 | Validation | 40
In Dev | 10 | In Dev | 20 | In Dev | 30 | In Dev | 40
Ready | 10 | Ready | 20 | Ready | 30 | Ready | 40
New | 10 | New | 20 | New | 30 | New | 40
Grand Total | 50 | Grand Total | 100 | Grand Total | 150 | Grand Total | 200
Grand Total | 50 | Grand Total | 100 | Grand Total | 150 | Grand Total | 200

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Sum of Story Points | Column Labels | [5 empty] | Historical
Row Labels | Alpha | ngStars | NW | SoftTeco | Titan | Grand Total | Sprint | Alpha | ngStars | NW | SoftTeco | Titan | QA | Total
Q1 |  |  | 30 |  |  | 30 | Q1 | 18.5 | 24.5 | 47.5 | 67.5 | 25.5 | 2.5 | 186
Q2 |  | 30 |  |  |  | 30 | Q2 | 18 | 70.5 | 63 | 61 |  | 13 | 225.5
Q3 | 30 |  |  |  |  | 30 | Q3 | 27 | 46.5 | 57.5 | 87 |  | 3 | 221
Q4 |  |  |  |  | 30 | 30 | Q4 | 21 | 41.5 | 27.5 | 61 |  | 1.5 | 152.5
Q5 |  |  |  | 30 |  | 30 | Q5 | 23.5 | 43.5 | 68.5 | 55.5 |  | 3 | 194
Q6 |  |  | 30 |  |  | 30 | Q6 | 24 | 32 | 60.5 | 102 |  |  | 218.5
Q7 |  | 30 |  |  |  | 30 | Q7 | 15.5 | 43 | 55.5 | 79 |  |  | 193
Q8 | 30 |  |  |  |  | 30 | Q8 | [6 empty] | 0
Q9 |  |  |  |  | 30 | 30 | Q9 | [6 empty] | 0
Q10 |  |  |  | 30 |  | 30 | Q10 | [6 empty] | 0
Q11 |  |  | 30 |  |  | 30 | Q11 | [6 empty] | 0
Q12 |  | 30 |  |  |  | 30 | Q12 | [6 empty] | 0
Q13 | 30 |  |  |  |  | 30 | Q13 | [6 empty] | 0
Q14 |  |  |  |  | 30 | 30 | Q14 | [6 empty] | 0
Grand Total | 90 | 90 | 90 | 60 | 90 | 420 | Total | 147.5 | 301.5 | 380 | 513 | 25.5 | 23 | 1390.5

## Active Sprint
6

## _ActiveSprintData (hidden)
Active Sprint | Quasar8 | Type | (Multiple Items)
|  | Last Sprint | Quasar8
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 1
|  | New | 1
|  | Cancelled | 1
|  | Grand Total | 6
|  | Grand Total | 6
|  | Chart Tital | Sprint 8 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()}
| Release | Quasar | Release | Quasar
| Type | Bug | Type | Bug
| Team Grouped | (Multiple Items) | Status | (Multiple Items)
| Status | (Multiple Items)
|  |  | Count of Key | Column Labels
| Row Labels | Count of Key | Row Labels | Highest | High | Medium | Low | Lowest | Grand Total
| Highest | 1 | Titan | 1 | 1 | 1 | 1 | 1 | 5
| High | 1 | Grand Total | 1 | 1 | 1 | 1 | 1 | 5
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | (All)
| Type | Bug
| Team Grouped | (Multiple Items)
| Status | Bug: Closed
| Row Labels | Count of Key
| Q1 | 1
Q2
Q3
Q4
| Q5 | 1
Q6
Q7
Q8
Q9
Q10
Q11
Q12
Q13
Q14
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Quasar Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-release-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(AE2, "uasar", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getQuasarComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))]</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | ngStars | Epic: New | [16 empty] | ngStars | [8 empty] | Pegasus1 |  | Pegasus |  | New | UME |  | ngStars | ngStars
key | Story |  | NW | Epic: Decomposition | [16 empty] | NW | [8 empty] | Pegasus2 |  | Quasar |  | Ready | Artifact List v2 |  | NW | NW
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | SoftTeco | Epic: Review | [16 empty] | SoftTeco | [8 empty] | Pegasus3 |  |  |  | In Dev | R&D Bucket |  | SoftTeco | SoftTeco
key | Tech Debt |  | Titan | Epic: Ready | [16 empty] | Titan | [8 empty] | Pegasus4 |  |  |  | Validation | Other |  | Titan | Titan
key | Bug |  | Alpha | Epic: In Development | [16 empty] | Alpha | [8 empty] | Pegasus5 |  |  |  | Closed |  |  | Alpha | Alpha
key |  |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Pegasus6 |  |  |  | Cancelled |  |  | Unassigned | Unassigned
key |  |  | TechComm | Epic: Cancelled | [16 empty] | TechComm | [8 empty] | Pegasus7 |  |  |  | Unkown |  |  | TechComm | TechComm
key |  |  | QA | Epic: Demo | [16 empty] | QA | [8 empty] | Pegasus8 | [6 empty] | QA | QA
key |  |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Quasar1 | Q1 | [5 empty] | DevOps | DevOps
key |  |  | Evolution | Story: Review | [16 empty] | Evolution | [8 empty] | Quasar2 | Q2
key | Story |  | No Pasaran | Story: Ready | [8 empty] | 20 | [7 empty] | No Pasaran | [8 empty] | Quasar3 | Q3
key |  |  | Status200 | Story: In Development | [16 empty] | Status200 | [8 empty] | Quasar4 | Q4
key |  |  |  | Story: Validation | [25 empty] | Quasar5 | Q5
key |  |  |  | Story: Demo Checkpoint | [25 empty] | Quasar6 | Q6
key |  |  |  | Story: Done | [25 empty] | Quasar7 | Q7
key |  |  |  | Story: In Development - On Hold | [25 empty] | Quasar8 | Q8
key |  |  |  | Story: Demo Checkpoint - On Hold | [25 empty] | Quasar9 | Q9
key |  |  |  | Story: Prototype Done | [25 empty] | Quasar10 | Q10
key |  |  |  | Story: Ready for Validation | [25 empty] | Quasar11 | Q11
key |  |  |  | Story: Validation - On Hold | [25 empty] | Quasar12 | Q12
key |  |  |  | Story: Cancelled | [25 empty] | Quasar13 | Q13
key |  |  |  | Tech Debt: New | [25 empty] | Quasar14 | Q14
key |  |  |  | Tech Debt: Review
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30
key |  |  |  | Tech Debt: In Development
key |  |  |  | Tech Debt: Validation
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | New
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | Ready
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | In Dev
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | Validation
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | Closed
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | Cancelled
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Quasar8 |  |  |  | Unkown
key |  |  |  | Tech Debt: Cancelled
key |  |  |  | Bug: New
key |  |  |  | Bug: Triage
key | Bug |  |  | Bug: Ready | [26 empty] | Q1 | Quasar | Highest |  |  |  | Titan
key | Bug |  |  | Bug: In Development | [26 empty] | Q2 | Quasar | High |  |  |  | Titan
key | Bug |  |  | Bug: Validation | [26 empty] | Q14 | Quasar | Medium |  |  |  | Titan
key | Bug |  |  | Bug: Closed | [26 empty] | Q5 | Quasar | Low |  |  |  | Titan
key | Bug |  |  | Bug: New - On Hold | [26 empty] | Q6 | Quasar | Lowest |  |  |  | Titan
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | Q7 | Quasar | Low |  |  |  | Titan
key |  |  |  | Bug: Validation - On Hold
key |  |  |  | Bug: Investigate
key
key | Bug |  |  | Bug: Closed | [26 empty] | Q1 | Quasar | Highest |  |  |  | Titan
key | Epic | [8 empty] | Artifact List |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Quasar | [6 empty] | 30 | 60 | 40
key | Epic | [8 empty] | Diagram Editor |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Quasar | [6 empty] | 30 | 60 | 40
key | Story |  |  | Story: New | [8 empty] | 10 | [18 empty] | Quasar |  | New |  |  | Alpha
key | Story |  |  | Story: Ready | [8 empty] | 10 | [18 empty] | Quasar |  | Ready |  |  | Alpha
key | Story |  |  | Story: In Development | [8 empty] | 10 | [18 empty] | Quasar |  | In Dev |  |  | Alpha
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Quasar |  | Validation |  |  | Alpha
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Quasar |  | Closed |  |  | Alpha
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Quasar |  | New |  |  | ngStars
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Quasar |  | Ready |  |  | ngStars
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Quasar |  | In Dev |  |  | ngStars
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Quasar |  | Validation |  |  | ngStars
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Quasar |  | Closed |  |  | ngStars
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Quasar |  | New |  |  | NW
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Quasar |  | Ready |  |  | NW
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Quasar |  | In Dev |  |  | NW
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Quasar |  | Validation |  |  | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Quasar |  | Closed |  |  | NW
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Quasar |  | New |  |  | SoftTeco
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Quasar |  | Ready |  |  | SoftTeco
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Quasar |  | In Dev |  |  | SoftTeco
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Quasar |  | Validation |  |  | SoftTeco
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Quasar |  | Closed |  |  | SoftTeco
key
key | Epic | [13 empty] | 200 | [16 empty] | Quasar |  |  | UME
key | Epic | [13 empty] | 200 | [16 empty] | Quasar |  |  | Artifact List v2
key | Epic | [13 empty] | 200 | [16 empty] | Quasar |  |  | R&D Bucket
key | Epic | [13 empty] | 200 | [16 empty] | Quasar |  |  | Other
key
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q1 | [5 empty] | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q2 | [5 empty] | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q3 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q4 | [5 empty] | Titan
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q5 | [5 empty] | SoftTeco
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q6 | [5 empty] | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q7 | [5 empty] | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q8 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q9 | [5 empty] | Titan
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q10 | [5 empty] | SoftTeco
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q11 | [5 empty] | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q12 | [5 empty] | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q13 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | Q14 | [5 empty] | Titan | [5 empty] | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _ReadinessData sheet:
* Update table B20 as above.
3. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
4. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
5. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).