## Release
2000

## CPM
200

## Excel Import
200

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [6 empty] | Release, CPM | Excel Import | Release | CPM | Excel Import | Release |  | CPM |  | Excel Import |  |  | Release | Rocket
Actual | 0% | Start Date | End Date | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 100% | 2018-10-24 | 2019-01-15 |  |  |  |  | 0% | 0% | 75% | 25% | 25% | 285 | 300 | 75 | 150 | 50 | 150 | 2018-12-25
|  |  | 2018-09-11 | R1 | 2018-10-24 | 2018-11-06 | 10 | 17.54% | 17.54% |  |  |  | 235 |  | 61.8421 |  | 41.2281 |  | 2018-12-26 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Release |  | Report Date ??? | ${bpHelper.getToday()} | R2 | 2018-11-07 | 2018-11-20 | 10 | 35.09% | 35.09% |  |  |  | 185 |  | 48.6842 |  | 32.4561 |  | 2019-01-01 | (blank) | 800
Actual | 75% | Report Date | 2018-10-22 | R3 | 2018-11-21 | 2018-12-04 | 10 | 52.63% | 52.63% |  |  |  | 135 |  | 35.5263 |  | 23.6842 |  |  | Cross Project Move | 200 | 150
Remainder | 25% |  |  | R4 | 2018-12-05 | 2018-12-18 | 10 | 70.18% | 70.18% |  |  |  | 85 |  | 22.3684 |  | 14.9123 |  |  | Excel Import | 200 | 150
|  |  |  | R5 | 2018-12-19 | 2019-01-01 | 7 | 82.46% | 82.46% |  |  |  | 50 |  | 13.1579 |  | 8.7719 |  |  | Grand Total | 1200 | 300
CPM |  |  |  | R6 | 2019-01-02 | 2019-01-15 | 10 | 100% | 100% |  |  |  | 0 |  | 0 |  | 0
Actual | 25%
Remainder | 75%
Excel Import
Actual | 25%
Remainder | 75%
Time Elapsed Excel Import
Actual | 0%
Remainder | 100%
|  | Release | Rocket | Release | Rocket |  |  |  | Feature | Cost
Release | Rocket | Type | Epic | Type | Epic |  |  |  | Release | 285
Type | Epic | ST:Components | Cross Project Move | ST:Components | Excel Import |  |  |  | CPM | 75
[9 empty] | Excel Import | 50
Values |  | Values |  | Values
Done | 900 | Done | 50 | Done | 50
In Validation | 80 | In Validation | 40 | In Validation | 40
In Dev | 120 | In Dev | 60 | In Dev | 60
Ready | 60 | Ready | 30 | Ready | 30
Not Decomposed | 840 | Not Decomposed | 20 | Not Decomposed | 20
Release | (blank) | Release | (blank) | Release | (blank)
Type | Epic | Type | Epic | Type | Epic
|  | ST:Components | Diagram Editor | ST:Components | Artifact List
Sum of Epic Total Estimate
| 2000 | Sum of Epic Total Estimate |  | Sum of Epic Total Estimate
|  |  | 200 |  | 200
Type | Epic
Release | Rocket
Row Labels | Sum of Epic Total Estimate
CPM | 200
Excel Import | 200
UME | 200
DevOps | 200
R&D Bucket | 200
Other | 200
Grand Total | 1200

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | CPM | [7 empty] | Excel Import
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
R0 |  |  | 1200 | 285 | 0 | 360 | 900 | 300 | 30% | 75% | 200 | 50 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 50 | 0 | 180 | 50 | 150 | 90% | 25%
R1 | 2018-10-24 | 2018-11-06 |  | 285 | [7 empty] | 50 | [7 empty] | 50
R2 | 2018-11-07 | 2018-11-20 |  | 285 | [7 empty] | 50 | [7 empty] | 50
R3 | 2018-11-21 | 2018-12-04 |  | 285 | [7 empty] | 50 | [7 empty] | 50
R4 | 2018-12-05 | 2018-12-18 |  | 285 | [7 empty] | 50 | [7 empty] | 50
R5 | 2018-12-19 | 2019-01-01 |  | 285 | [7 empty] | 50 | [7 empty] | 50 | [6 empty] | Release | Rocket
R6 | 2019-01-02 | 2019-01-15 |  | 285 | [7 empty] | 50 | [7 empty] | 50
Column Labels
Epic
[27 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
[27 empty] | (blank) | 800
[27 empty] | Cross Project Move | 200 |  | 180 | 150
[27 empty] | Excel Import | 200 |  | 180 | 150
[27 empty] | Grand Total | 1200 |  | 360 | 300

## _ReadinessData (hidden)
|  |  | Release | Rocket
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate
Epic | 840 |  | Row Labels | Sum of Story Points
Grand Total | 840 |  | Grand Total
Sprint | Epics New | Stories Ready
P1 | 840 | 0
P2
P3
P4
P5
P6

## Team Backlog
500

## _TeamBacklogData (hidden)
Release | Rocket
Type | (Multiple Items)
Team Grouped | (All)
Row Labels | Sum of Story Points
Closed | 100
Validation | 100
In Dev | 100
Ready | 100
New | 100
Grand Total | 500
Grand Total | 500

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Row Labels | Sum of Story Points | Historical
P1 | 90 | Sprint | R&D | Total
P2 | 90 | P1 |  | 0
P3 | 60 | P2 |  | 0
P4 | 60 | P3 |  | 0
P5 | 60 | P4 |  | 0
P6 | 60 | P5 |  | 0
Grand Total | 420 | P6 |  | 0
|  | Total | 0 | 0

## Active Sprint
6

## _ActiveSprintData (hidden)
Active Sprint | Rocket1 | Type | (Multiple Items)
|  | Last Sprint | Rocket1
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 1
|  | New | 1
|  | Cancelled | 1
Unkown
|  | Grand Total | 6
|  | Grand Total | 6
|  | Chart Tital | Sprint Rocket1 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()}
| Release | Rocket
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Rocket
| Type | Bug
| Team Grouped | (All)
| Status | Bug: Closed
| Row Labels | Count of Key
| P1 | 1
P2
P3
| P4 | 1
P5
P6
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Rocket Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-rocket-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(SUBSTITUTE(AE2, "ocket", ""), "uasar", ""), "egasus", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getRocketComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | ngStars | Epic: New | [16 empty] | ngStars | [8 empty] | Rocket1 |  | Rocket |  | New | UME |  | ngStars | ngStars
key | Story |  | NW | Epic: Decomposition | [8 empty] | 5 | [7 empty] | NW | [8 empty] | Rocket2 |  |  |  | Ready | CPM |  | NW | NW | [5 empty] | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | SoftTeco | Epic: Review | [8 empty] | 10 | [7 empty] | SoftTeco | [8 empty] | Rocket3 |  |  |  | In Dev | Excel Import |  | RD | SoftTeco | [5 empty] | Yes
key | Tech Debt |  | Titan | Epic: Ready | [8 empty] | 20 | [7 empty] | Titan | [8 empty] | Rocket4 |  |  |  | Validation | DevOps |  | Titan | Titan | [5 empty] | Yes
key | Bug |  | Alpha | Epic: In Development | [16 empty] | Alpha | [8 empty] | Rocket5 |  |  |  | Closed | R&D Bucket |  | Alpha | Alpha | [5 empty] | No
key | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Rocket6 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [5 empty] | No
key | DevOps |  | TechComm | Epic: Cancelled | [16 empty] | TechComm | [8 empty] | Rocket1 |  |  |  | Unkown |  |  | RD | TechComm | [5 empty] | No
key | DevOps |  | QA | Epic: Demo | [16 empty] | QA | [8 empty] | Rocket2 | [6 empty] | QA | QA
key | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Rocket3 | P1 | [5 empty] | DevOps | DevOps
key |  |  | Evolution | Story: Review | [16 empty] | Evolution | [8 empty] | Rocket4 | P2
key | Story |  | No Pasaran | Story: Ready | [8 empty] | 20 | [7 empty] | No Pasaran | [8 empty] | Rocket5 | P3 | [12 empty] | Yes
key |  |  | Status200 | Story: In Development | [16 empty] | Status200 | [8 empty] | Rocket6 | P4
key |  |  |  | Story: Validation | [25 empty] | Rocket1 | P5
key |  |  |  | Story: Demo Checkpoint | [25 empty] | Rocket2 | P6
key |  |  |  | Story: Done | [25 empty] | Rocket3 | P1
key |  |  |  | Story: In Development - On Hold | [25 empty] | Rocket4 | P2
key |  |  |  | Story: Demo Checkpoint - On Hold | [25 empty] | Rocket5 | P3
key |  |  |  | Story: Prototype Done | [25 empty] | Rocket6 | P4
key |  |  |  | Story: Ready for Validation | [25 empty] | Rocket1 | P5
key |  |  |  | Story: Validation - On Hold | [25 empty] | Rocket2 | P6
key |  |  |  | Story: Cancelled | [25 empty] | Rocket3 | P1
key |  |  |  | Tech Debt: New | [25 empty] | Rocket4 | P1
key |  |  |  | Tech Debt: Review
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30
key |  |  |  | Tech Debt: In Development
key |  |  |  | Tech Debt: Validation
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | New
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | Ready
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | In Dev
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | Validation
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | Closed
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | Cancelled
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Rocket1 |  |  |  | Unkown
key |  |  |  | Tech Debt: Cancelled
key |  |  |  | Bug: New
key |  |  |  | Bug: Triage
key | Bug |  |  | Bug: Ready | [26 empty] | P1 | Rocket | Highest |  |  |  | Titan
key | Bug |  |  | Bug: In Development | [26 empty] | P2 | Rocket | High |  |  |  | Titan
key | Bug |  |  | Bug: Validation | [26 empty] | P3 | Rocket | Medium |  |  |  | Titan
key | Bug |  |  | Bug: Closed | [26 empty] | P4 | Rocket | Low |  |  |  | Titan
key | Bug |  |  | Bug: New - On Hold | [26 empty] | P5 | Rocket | Lowest |  |  |  | Titan
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | P6 | Rocket | Low |  |  |  | Titan
key |  |  |  | Bug: Validation - On Hold
key |  |  |  | Bug: Investigate
key
key | Bug |  |  | Bug: Closed | [26 empty] | P1 | Rocket | Highest |  |  |  | Titan
key | Epic | [8 empty] | Cross Project Move |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Rocket |  |  | DevOps |  |  |  | 30 | 60 | 40
key | Epic | [8 empty] | Excel Import |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Rocket |  |  | Excel Import |  |  |  | 30 | 60 | 40
key | Story |  |  | Story: New | [5 empty] | Artifact List |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | New |  |  | Alpha
key | Story |  |  | Story: Ready | [5 empty] | Diagram Editor |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | Ready |  |  | Alpha
key | Story |  |  | Story: In Development | [5 empty] | DevOps |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | In Dev |  |  | Alpha
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Rocket |  | Validation |  |  | Alpha
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Rocket |  | Closed |  |  | Alpha
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Rocket |  | New |  |  | ngStars
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Rocket |  | Ready |  |  | ngStars
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Rocket |  | In Dev |  |  | ngStars
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Rocket |  | Validation |  |  | ngStars
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Rocket |  | Closed |  |  | ngStars
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Rocket |  | New |  |  | NW
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Rocket |  | Ready |  |  | NW
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Rocket |  | In Dev |  |  | NW
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Rocket |  | Validation |  |  | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Rocket |  | Closed |  |  | NW
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Rocket |  | New |  |  | RD
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Rocket |  | Ready |  |  | RD
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Rocket |  | In Dev |  |  | RD
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Rocket |  | Validation |  |  | RD
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Rocket |  | Closed |  |  | RD
key
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | UME
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | CPM
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | R&D Bucket
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | Other
key | [31 empty] | Rocket |  |  | Excel Import
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P1 | Rocket |  |  | DevOps |  | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P2 | Rocket |  |  |  |  | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P3 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P4 | [5 empty] | Titan
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P5 | [5 empty] | RD
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P6 | [5 empty] | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P1 | [5 empty] | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P2 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P3 | [5 empty] | Titan
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P4 | [5 empty] | RD
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P5 | [5 empty] | NW
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P6 | [5 empty] | ngStars
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P1 | [5 empty] | Alpha
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | P2 | [5 empty] | Titan
key
key | DevOps |  |  | DevOps: New
key | DevOps |  |  | DevOps: Review
key | DevOps |  |  | DevOps: Ready
key | DevOps |  |  | DevOps: In Development
key | DevOps |  |  | DevOps: Validation
key | DevOps |  |  | DevOps: Demo Checkpoint
key | DevOps |  |  | DevOps: Done
key | DevOps |  |  | DevOps: In Development - On Hold
key | DevOps |  |  | DevOps: Demo Checkpoint - On Hold
key | DevOps |  |  | DevOps: Prototype Done
key | DevOps |  |  | DevOps: Ready for Validation
key | DevOps |  |  | DevOps: Validation - On Hold
key | DevOps |  |  | DevOps: Cancelled | [39 empty] | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).