## Notes
1. The remaining scope based on Estimate in Days of not closed Epics is pessimistic because some Stories/Spikes/Tech Debts that are already closed are not taken into account.
2. The remaining scope based on Story Points of not closed Stories/Spikes/Tech Debts is optimistic because not all Epics are decomposed.
3. The remaining scope based on Epic Remaining Estimate (a script field) of not closed Epics is more realistic. The Epic Remaining Estimate field is calculated as follows:
* 0 for closed Epics.
* The Story Points of closed Stories/Spikes/Tech Debts are deducted from the Epic Total Estimate (another script field), which is calculated as:
* For Epics before Ready status - Max of Estimate in Days of the Epic and Story Points of all not cancelled Stories/Spikes/Tech Debts.
* For Epics in Ready status or further, except Done - Story Points of all not cancelled Stories/Spikes/Tech Debts. Here we assume that the Epic is decomposed and the cost of Stories/Spikes/Tech Debts has precedence over the cost of the Epic itself.
4. Stories/Spikes/Tech Debt are Decomposed if they are in Ready status or further.
5. Epic Decomposition Progress is calculated as the ratio of Story Estimate to Total Estimate.
6. Story Decomposition Progress is calculated as the ratio of Decomposed to Total Estimate.

## Bugs
Not Closed Bugs (TechComm excluded)
Release | Quasar
Type | Bug
Team | Bug Count | Sum of Story Points
Grand Total

## Development
Remaining Scope based on Epics - Estimate in Days (see Notes - 1) |  |  | Remaining Scope based on Stories/Spikes/Tech Debts - Story Points (see Notes - 2) |  |  |  |  | Remaining Scope based on Epics - Epic Remaining and Total Estimate (see Notes - 3)
Release | Quasar |  | Release | Quasar |  |  |  | Release | Quasar
Status | (Multiple Items) |  | Status | (Multiple Items) |  |  |  | Status | (Multiple Items)
Sum of Estimate in Days | Column Labels |  | Sum of Story Points | Column Labels |  |  |  |  | Column Labels
Team |  |  | Team | Grand Total
Alpha |  |  | Alpha |  |  |  |  | Team |  | Remaining Estimate
DevOps |  |  | DevOps |  |  |  |  | Alpha |  | $[K8 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J8), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J8), 0)]
ngStars |  |  | ngStars |  |  |  |  | ngStars |  | $[K9 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J9), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J9), 0)]
NW |  |  | NW |  |  |  |  | NW |  | $[K10 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J10), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J10), 0)]
QA |  |  | QA |  |  |  |  | QA |  | $[K11 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J11), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J11), 0)]
SoftTeco |  |  | SoftTeco |  |  |  |  | SoftTeco |  | $[K12 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J12), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J12), 0)]
TechComm |  |  | TechComm |  |  |  |  | Titan |  | $[K13 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J13), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J13), 0)]
Titan |  |  | Titan |  |  |  |  | Unassigned |  | $[K14 + IFERROR(GETPIVOTDATA("Different Story Points", $A$41, "Team Grouped", J14), 0) - IFERROR(GETPIVOTDATA("Different Story Points", $G$41, "Epic Team Grouped", J14), 0)]
Unassigned |  |  | Unassigned |  |  |  |  | Grand Total |  | 0
(blank) |  |  | (blank)
Grand Total |  |  | Grand Total
Backlog Health - Stories in Ready status
Release | (Multiple Items)
Backlog Health | Yes
Column Labels
| Spike |  | Story |  | Total Count | Total SPs
Team | Count | SPs | Count | SPs
NW |  |  | 1 | 5 | 1 | 5
SoftTeco | 1 | 10 |  |  | 1 | 10
Grand Total | 1 | 10 | 1 | 5 | 2 | 15
Story Points In | [5 empty] | Story Points Out
Release | Quasar |  |  |  |  | Release | Quasar
Status | (Multiple Items) |  |  |  |  | Status | (Multiple Items)
Sum of Different Story Points | Column Labels |  |  |  |  | Sum of Different Story Points | Column Labels
Team | Grand Total |  |  |  |  | Team | Grand Total
Grand Total | [5 empty] | Grand Total

## Features
Feature Decomposition and Development progress (see Notes - 4-6)
Release | Quasar
Team | (All)
Column Labels
Component
Grand Total

## Issues
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Release | Priority | Customer | Team Grouped | Epic Team Grouped | Epic Fully Decomposed | Different Story Points | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-release-planning-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${issue.fixVersions.name} | ${issue.priority.name} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | ngStars | Epic: New | [16 empty] | ngStars | [8 empty] | Pegasus |  |  | ngStars | ngStars |  |  | Yes
key | Story |  | NW | Epic: Decomposition | [8 empty] | 5 | [7 empty] | NW | [8 empty] | Quasar |  |  | NW | NW |  |  | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | SoftTeco | Epic: Review | [8 empty] | 10 | [7 empty] | SoftTeco | [8 empty] | Rocket |  |  | SoftTeco | SoftTeco |  |  | Yes
key | Tech Debt |  | Titan | Epic: Ready | [8 empty] | 20 | [7 empty] | Titan | [11 empty] | Titan | Titan |  |  | Yes
key | Bug |  | Alpha | Epic: In Development | [16 empty] | Alpha | [11 empty] | Alpha | Alpha |  |  | Yes
key |  |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [11 empty] | Unassigned | Unassigned |  |  | Yes
key |  |  | TechComm | Epic: Cancelled | [16 empty] | TechComm | [11 empty] | TechComm | TechComm
key |  |  | QA | Epic: Demo | [16 empty] | QA | [11 empty] | QA | QA
key |  |  | DevOps | Story: New | [16 empty] | DevOps | [11 empty] | DevOps | DevOps
key |  |  | Evolution | Story: Review | [16 empty] | Evolution
key |  |  | No Pasaran | Story: Ready | [16 empty] | No Pasaran
key |  |  | Status200 | Story: In Development | [16 empty] | Status200
key |  |  |  | Story: Validation
key |  |  |  | Story: Demo Checkpoint
key |  |  |  | Story: Done
key |  |  |  | Story: In Development - On Hold
key |  |  |  | Story: Demo Checkpoint - On Hold
key |  |  |  | Story: Prototype Done
key |  |  |  | Story: Ready for Validation
key |  |  |  | Story: Validation - On Hold
key |  |  |  | Story: Cancelled
key |  |  |  | Tech Debt: New
key |  |  |  | Tech Debt: Review
key |  |  |  | Tech Debt: Ready
key |  |  |  | Tech Debt: In Development
key |  |  |  | Tech Debt: Validation
key |  |  |  | Tech Debt: Demo Checkpoint
key |  |  |  | Tech Debt: Done
key |  |  |  | Tech Debt: In Development - On Hold
key |  |  |  | Tech Debt: Demo Checkpoint - On Hold
key |  |  |  | Tech Debt: Prototype Done
key |  |  |  | Tech Debt: Ready for Validation
key |  |  |  | Tech Debt: Validation - On Hold
key |  |  |  | Tech Debt: Cancelled
key |  |  |  | Bug: New
key |  |  |  | Bug: Triage
key |  |  |  | Bug: Ready
key |  |  |  | Bug: In Development
key |  |  |  | Bug: Validation
key |  |  |  | Bug: Closed
key |  |  |  | Bug: New - On Hold
key |  |  |  | Bug: In Development - On Hold
key |  |  |  | Bug: Validation - On Hold
key |  |  |  | Bug: Investigate | [32 empty] | </jt:forEach>

## Sprint Metrics
|  |  | Release | [7 empty] | UME | [7 empty] | Artifact List v2
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
P8 |  |  | 2023 | 2380 | 938.5 | 411.5 | 0 | 2023 | 20.34% | 0% | 918 | 1400 | 141 | 83 | 0 | 918 | 9.041% | 0% | 575 | 700 | 350 | 215 | 0 | 575 | 37.39% | 0%
Q1 | 2018-04-04 | 2018-04-17 | 2442 | 2380 | 1008 | 569.5 | 117.5 | 2324.5 | 23.32% | 4.812% | 1327 | 1400 | 273 | 134 | 53 | 1274 | 10.1% | 3.994% | 696 | 700 | 389 | 261 | 42 | 654 | 37.5% | 6.034%
Q2 | 2018-04-18 | 2018-05-01 | 2743.8 | 2380 | 2218.3 | 811 | 344.5 | 2399.3 | 29.56% | 12.56% | 1672.3 | 1400 | 1213.3 | 268 | 128 | 1544.3 | 16.03% | 7.654% | 645 | 700 | 615 | 365 | 119.5 | 525.5 | 56.59% | 18.53%
Q3 | 2018-05-02 | 2018-05-15 | 2412 | 2380 | 2128.5 | 974 | 552.5 | 1859.5 | 40.38% | 22.91% | 1479 | 1400 | 1226.5 | 336.5 | 211.5 | 1267.5 | 22.75% | 14.3% | 665.5 | 700 | 635.5 | 464 | 203.5 | 462 | 69.72% | 30.58%
Q4 | 2018-05-16 | 2018-05-29 | 2437.5 | 2380 | 2265 | 1172.5 | 696.5 | 1741 | 48.1% | 28.57% | 1427.5 | 1400 | 1283 | 392 | 266.5 | 1161 | 27.46% | 18.67% | 734 | 700 | 707 | 597.5 | 276 | 458 | 81.4% | 37.6%
Q5 | 2018-05-30 | 2018-06-12 | 2462.5 | 2380 | 2354.5 | 1363.5 | 865.5 | 1597 | 55.37% | 35.15% | 1400.5 | 1400 | 1336.5 | 476.5 | 368 | 1032.5 | 34.02% | 26.28% | 763 | 700 | 726 | 675 | 335.5 | 427.5 | 88.47% | 43.97%
Q6 | 2018-06-13 | 2018-06-26 | 2257 | 2380 | 2157.5 | 1478 | 1072.5 | 1184.5 | 65.49% | 47.52% | 1190.5 | 1400 | 1130 | 558.5 | 447 | 743.5 | 46.91% | 37.55% | 764 | 700 | 733 | 682 | 442.5 | 321.5 | 89.27% | 57.92%
Q7 | 2018-06-27 | 2018-07-10 | 2264.5 | 2380 | 2177 | 1563.5 | 1263.5 | 1001 | 69.04% | 55.8% | 1171 | 1400 | 1113.5 | 614 | 537 | 634 | 52.43% | 45.86% | 777 | 700 | 755 | 704 | 527.5 | 249.5 | 90.6% | 67.89%
Q8 | 2018-07-11 | 2018-07-17 | 2220.5 | 2380 | 2144 | 1699.5 | 1310.5 | 910 | 76.54% | 59.02% | 1106 | 1400 | 1050.5 | 709 | 579.5 | 526.5 | 64.1% | 52.4% | 787 | 700 | 777 | 734 | 527.5 | 259.5 | 93.27% | 67.03%
Q9 | 2018-07-18 | 2018-07-31 | 2306.5 | 2380 | 2212 | 1865.5 | 1513.5 | 793 | 80.88% | 65.62% | 1077 | 1400 | 1053.5 | 827.5 | 675.5 | 401.5 | 76.83% | 62.72% | 872.5 | 700 | 822.5 | 751.5 | 615.5 | 257 | 86.13% | 70.54%
Q10 | 2018-08-01 | 2018-08-14 | 2432.5 | 2380 | 2284.5 | 2016.5 | 1707 | 725.5 | 82.9% | 70.17% | 1086.5 | 1400 | 1064.5 | 885 | 776.5 | 310 | 81.45% | 71.47% | 944 | 700 | 874 | 822.5 | 693.5 | 250.5 | 87.13% | 73.46%
Q11 | 2018-08-15 | 2018-08-28 | #REF! | 2380 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1400 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 700 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Q12 | 2018-08-29 | 2018-09-11 |  | 2380 | [7 empty] | 1400 | [7 empty] | 700
Q13 | 2018-09-12 | 2018-09-25 |  | 2380 | [7 empty] | 1400 | [7 empty] | 700
Q14 | 2018-09-26 | 2018-10-09 |  | 2380 | [7 empty] | 1400 | [7 empty] | 700