## Release
3580.25
70

## CPM
200

## Excel Import
200

## UME v2
380
380

## _ReleaseData (hidden)
Time Elapsed | <mt:execute script="blueprint-helper.groovy"/> | [7 empty] | Release, CPM, UME v2 | Excel Import | Release | CPM | Excel Import | UME v2 | Release |  | CPM |  | Excel Import |  | UML v2 |  |  | Release | Rocket
Actual | 35.09% | Start Date | End Date |  | Dev Sprint | Start Date | End Date | Work Days | Ideal Progress | Ideal Progress | Actual Progress | Actual Progress | Actual Progress | Actual Progress | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Ideal Burndown | Actual Burndown | Stabilization and Holidays | Type | Epic
Remainder | 64.91% | 2018-10-24 | 2019-01-15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 285 | 469 | 50 | 44 | 50 | 48 | 75 | 168 | 2018-12-25 | Not DevOps | Yes
|  |  | 2018-09-11 |  | R1 | 2018-10-24 | 2018-11-06 | 10 | 17.54% | 17.54% | 15.1% | 16% | 23% | 24% | 235 | 306.8 | 41.2281 | 37 | 41.2281 | 37 | 61.8421 | 72.8 | 2018-12-26
Release |  | Report Date ??? | ${bpHelper.getToday()} |  | R2 | 2018-11-07 | 2018-11-20 | 10 | 35.09% | 35.09% | 77.5% | 25% | 25% | 25% | 185 | 450 | 32.4561 | 150 | 32.4561 | 150 | 48.6842 | 150 | 2019-01-01 | Row Labels | Sum of Epic Total Estimate | Sum of Epic Remaining Estimate
Actual | 77.5% | Report Date | 2018-11-20 |  | R3 | 2018-11-21 | 2018-12-04 | 10 | 52.63% | 52.63% |  |  |  |  | 135 |  | 23.6842 |  | 23.6842 |  | 35.5263 |  |  | (blank) | 1400.125
Remainder | 22.5% |  |  |  | R4 | 2018-12-05 | 2018-12-18 | 10 | 70.18% | 70.18% |  |  |  |  | 85 |  | 14.9123 |  | 14.9123 |  | 22.3684 |  |  | Diagram Editor | 200 | 150
[5 empty] | R5 | 2018-12-19 | 2019-01-01 | 7 | 82.46% | 82.46% |  |  |  |  | 50 |  | 8.7719 |  | 8.7719 |  | 13.1579 |  |  | Cross Project Move | 200 | 150
CPM |  |  |  |  | R6 | 2019-01-02 | 2019-01-15 | 10 | 100% | 100% |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Excel Import | 200 | 150
Actual | 25% | [22 empty] | Grand Total | 2000.125 | 450
Remainder | 75%
Excel Import
Actual | 25%
Remainder | 75%
UME v2
Actual | 25%
Remainder | 75%
Time Elapsed Excel Import
Actual | 35.09%
Remainder | 64.91%
|  | Release | Rocket |  | Release | Rocket |  | Release | Rocket |  |  |  |  | Feature | Cost
Release | Rocket | Type | Epic |  | Type | Epic |  | Type | Epic |  |  |  |  | Release | 285
Type | Epic | ST:Components | Cross Project Move |  | ST:Components | Excel Import |  | ST:Components | Diagram Editor |  |  |  |  | CPM | 50
Not DevOps | Yes | Not DevOps | Yes |  | Not DevOps | Yes |  | Not DevOps | Yes |  |  |  |  | Excel Import | 50
[14 empty] | UME v2 | 75
Values |  | Values |  |  | Values |  |  | Values
Done | 1550.125 | Done | 50 |  | Done | 50 |  | Done | 50
In Validation | 120 | In Validation | 40 |  | In Validation | 40 |  | In Validation | 40
In Dev | 180 | In Dev | 60 |  | In Dev | 60 |  | In Dev | 60
Ready | 90 | Ready | 30 |  | Ready | 30 |  | Ready | 30
Not Decomposed | 1640.125 | Not Decomposed | 20 |  | Not Decomposed | 20 |  | Not Decomposed | 200
Release | (blank)
Type | Epic | Release | Rocket |  | Release | Rocket |  | Release | Rocket
Not DevOps | Yes | Type | Epic |  | Type | Epic |  | Type | Epic
|  | ST:Components | Cross Project Move |  | ST:Components | Excel Import |  | ST:Components | Diagram Editor
Sum of Epic Total Estimate
| 3580.25 | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate |  |  | Sum of Epic Total Estimate
|  | 200 | 200 |  | 200 | 200 |  | 200 | 380
|  |  | Type | DevOps
Type | Epic
Release | Rocket |  | Row Labels | Sum of Story Points
Not DevOps | Yes |  | Development/Internal Support | 10
|  |  | Planned - Deployment and Release | 10
Row Labels | Sum of Epic Total Estimate |  | Planned - Operational Efficiency | 10
CPM | 200 |  | Planned - Platform Health | 10
Excel Import | 400 |  | Planned - Security | 10
UME v2 | 400 |  | Production Support | 10
CI/CD | 200.125 |  | Time Off / Conferences | 10
DevOps | 400 |  | (blank)
R&D Bucket | 200 |  | Grand Total | 70
Other | 200
Grand Total | 2000.125
| 2000.125 |  |  | 70

## _CumulativeFlowData (hidden)
|  |  | Release | [7 empty] | CPM | [7 empty] | Excel Import | [7 empty] | UME v2
Sprint | Start Date | End Date | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress | Total Estimate | Planned | Epic Decomposed | Story Decomposed | Completed | Remaining Estimate | Story Decomposition Progress | Development Progress
|  |  | 469 | 285 | 307 | 165 | 0 | 469 | 35.18% | 0% | 44 | 50 | 44 | 44 | 0 | 44 | 100% | 0% | 48 | 50 | 48 | 41 | 0 | 48 | 85.42% | 0% | 168 | 75 | 96 | 23 | 0 | 168 | 13.69% | 0%
R1 | 2018-10-24 | 2018-11-06 | 360.8 | 285 | 290.3 | 230.3 | 54 | 306.8 | 63.83% | 14.97% | 44 | 50 | 44 | 44 | 7 | 37 | 100% | 15.91% | 48 | 50 | 48 | 41 | 11 | 37 | 85.42% | 22.92% | 95.8 | 75 | 80.3 | 60.3 | 23 | 72.8 | 62.94% | 24.01%
R2 | 2018-11-07 | 2018-11-20 | 2000.125 | 285 | 0 | 360 | 1550.125 | 450 | 18% | 77.5% | 200 | 50 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 50 | 0 | 180 | 50 | 150 | 90% | 25% | 200 | 75 | 0 | 0 | 50 | 150 | 0% | 25%
R3 | 2018-11-21 | 2018-12-04 |  | 285 | [7 empty] | 50 | [7 empty] | 50 | [7 empty] | 75
R4 | 2018-12-05 | 2018-12-18 |  | 285 | [7 empty] | 50 | [7 empty] | 50 | [7 empty] | 75 | [6 empty] | Release | Rocket
R5 | 2018-12-19 | 2019-01-01 |  | 285 | [7 empty] | 50 | [7 empty] | 50 | [7 empty] | 75 | [6 empty] | Not DevOps | Yes
R6 | 2019-01-02 | 2019-01-15 |  | 285 | [7 empty] | 50 | [7 empty] | 50 | [7 empty] | 75
Column Labels
Epic
[35 empty] | Row Labels | Sum of Epic Total Estimate | Sum of Stories Estimate | Sum of Epic Decomposed | Sum of Epic Remaining Estimate
[35 empty] | Diagram Editor | 200 |  |  | 150
[35 empty] | (blank) | 1400.125
[35 empty] | Cross Project Move | 200 |  | 180 | 150
[35 empty] | Excel Import | 200 |  | 180 | 150
[35 empty] | Grand Total | 2000.125 |  | 360 | 450

## _ReadinessData (hidden)
Not DevOps | Yes |  | Release | Rocket
|  |  | Backlog Health | Yes
Row Labels | Sum of Epic Not Decomposed Estimate |  | Not DevOps | Yes
Epic | 1640.125
Grand Total | 1640.125 |  | Row Labels | Sum of Story Points
Grand Total
Sprint | Epics New | Stories Ready
P1 | 130.5 | 137.25
P2 | 1640.125 | 0
P3
P4
P5
P6

## Team Backlog
490

## _TeamBacklogData (hidden)
Release | Rocket
Type | (Multiple Items)
Team Grouped | (All)
Not DevOps | Yes
Row Labels | Sum of Story Points
Closed | 100
Validation | 100
In Dev | 100
Ready | 100
New | 90
Grand Total | 490
Grand Total | 490

## _TeamVelocityData (hidden)
Type | (Multiple Items)
Status | (Multiple Items)
Not DevOps | Yes
Row Labels | Sum of Story Points | Historical
R1 | 70 | Sprint | R&D | Total
R2 | 60 | R1 | 61 | 61
R3 | 60 | R2 |  | 0
R4 | 60 | R3 |  | 0
R5 | 60 | R4 |  | 0
R6 | 60 | R5 |  | 0
Grand Total | 370 | R6 |  | 0
|  | Total | 61 | 61

## Active Sprint
21

## _ActiveSprintData (hidden)
Active Sprint | Rocket2 | Type | (Multiple Items)
|  | Last Sprint | Rocket2
|  | Not DevOps | Yes
|  | Row Labels | Sum of Story Points
|  | Closed | 1
|  | Validation | 1
|  | In Dev | 1
|  | Ready | 6
|  | New | 1
|  | Cancelled | 1
|  | (blank) | 10
|  | Grand Total | 21
|  | Grand Total | 21
|  | Chart Tital | Sprint Rocket2 Progress

## Bugs
Bugs to Triage: ${bpHelper.getBugToTriageCount()}

## _BugsData (hidden)
<mt:execute script="blueprint-helper.groovy"/>
Bugs to Triage: ${bpHelper.getBugToTriageCount()}
| Release | Rocket
| Type | Bug
| Team Grouped | (All)
| Status | (Multiple Items)
| Row Labels | Count of Key
| Highest | 1
| High | 1
| Medium | 1
| Low | 1
| Lowest | 1
| Grand Total | 5
| Grand Total | 5
| Release | Rocket
| Type | Bug
| Team Grouped | (All)
| Status | Bug: Closed
| Row Labels | Count of Key
| R1 | 1
R2
R3
| R4 | 1
R5
R6
| Grand Total | 2

## Issues (hidden)
Key | Type | Summary | Team | Status | Sprints | Assignee | Reporter | Role: PM | Updated | ST:Components | Labels | Estimate in Days | Story Points | Stories Estimate | Epic Total Estimate | Epic Remaining Estimate | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Epic Link | Epic Team | Epic Decomposed | Epic Progress | Commitment Sprint | Cycle Time in Days | Development Time in Days | Ready For Validation Time in Days | Validation Time in Days | Last Commitment Sprint | Last Sprint | Sprint Label | Release | Priority | State | Rocket Component | Customer | Team Grouped | Epic Team Grouped | Epic Ready Estimate | Epic In Dev Estimate | Epic Validation Estimate | Epic Fully Decomposed | Different Story Points | DevOps Type | Not DevOps | Backlog Health | <mt:execute script="field-helper-tool.groovy"/><mt:execute script="blueprint-helper.groovy"/><mt:execute script="blueprint-rocket-dashboard-helper.groovy"/>
<jt:forEach items="${issues}" var="issue"><jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.key}"/> | ${issue.issueType.name} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${issue.key}" value="${issue.summary}"/> | ${fieldHelper.getFieldValueByName(issue, "Team")} | ${issue.statusObject.name} | ${bpHelper.getCollectionField(issue, "Sprint")} | ${issue.assigneeUser.displayName} | ${issue.reporterUser.displayName} | ${fieldHelper.getFieldValueByName(issue, "Role: PM")} | ${fieldHelper.getFieldValue(issue, "updated")} | ${fieldHelper.getFieldValueByName(issue, "ST:Components")} | ${bpHelper.getLabels(issue)} | ${fieldHelper.getFieldValueByName(issue, "Estimate in Days")} | ${fieldHelper.getFieldValueByName(issue, "Story Points")} | ${fieldHelper.getFieldValueByName(issue, "Stories Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Total Estimate")} | ${fieldHelper.getFieldValueByName(issue, "Epic Remaining Estimate")} | ${bpHelper.getAggregateOriginalEstimateInHours(issue)} | ${bpHelper.getAggregateRemainingEstimateInHours(issue)} | ${bpHelper.getAggregateTimeSpentInHours(issue)} | <jt:hyperlink address="${requestContext.canonicalBaseUrl}/browse/${bpHelper.getEpicLinkKey(issue)}" value="${fieldHelper.getFieldValueByName(issue, 'Epic Link')}"/> | ${fieldHelper.getFieldValueByName(issue, "Epic Team")} | ${bpHelper.getDecomposedEstimate(issue)} | ${bpHelper.getEpicProgress(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getCycleTime(issue)} | ${bpHelper.getDevelopmentTime(issue)} | ${bpHelper.getReadyForValidationTime(issue)} | ${bpHelper.getValidationTime(issue)} | ${bpHelper.getLastCommitmentSprint(issue)} | ${bpHelper.getLastSprint(issue)} | $[SUBSTITUTE(SUBSTITUTE(SUBSTITUTE(AE2, "ocket", ""), "uasar", ""), "egasus", "")] | ${issue.fixVersions.name} | ${issue.priority.name} | ${bpHelper.getState(issue)} | ${bpHelper.getRocketComponent(issue)} | ${fieldHelper.getFieldValueByName(issue, "Customer")} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Team"))} | ${bpHelper.getGroupedTeam(fieldHelper.getFieldValueByName(issue, "Epic Team"))} | ${bpHelper.getReadyEstimate(issue)} | ${bpHelper.getInDevEstimate(issue)} | ${bpHelper.getValidationEstimate(issue)} | $[IF(B2="Epic", IF(AND(IFERROR(VALUE(P2), 0)>0, P2=W2), "Yes", "No"), "")] | $[IF(OR(B2="Bug", B2="Epic"),"",IF(D2=V2, 0, N2))] | ${bpHelper.getDevOpsType(issue)} | $[IF(K2="DevOps","","Yes")] | ${bpHelper.isInBacklogHealth(issue)}</jt:forEach> | <mt:autosize columns="false"/>
<jt:forEach items="${issues.subList(0, 0)}" var="issue" where="${issue.key = ''}">
key | Epic |  | ngStars | Epic: New | [16 empty] | ngStars | [8 empty] | Rocket1 |  | Rocket |  | New | UME v2 |  | ngStars | ngStars | [6 empty] | Yes
key | Story |  | NW | Epic: Decomposition | [8 empty] | 5 | [7 empty] | NW | [8 empty] | Rocket2 |  |  |  | Ready | CPM |  | NW | NW | [6 empty] | Yes | Yes
key | Spike | NEEDS FOR FILTERING IN PIVOT TABLES | SoftTeco | Epic: Review | [8 empty] | 10 | [7 empty] | SoftTeco | [8 empty] | Rocket3 |  |  |  | In Dev | Excel Import |  | RD | SoftTeco | [6 empty] | Yes | Yes
key | Tech Debt |  | Titan | Epic: Ready | [8 empty] | 20 | [7 empty] | Titan | [8 empty] | Rocket4 |  |  |  | Validation | DevOps |  | Titan | Titan | [6 empty] | Yes | Yes
key | Bug |  | Alpha | Epic: In Development | [16 empty] | Alpha | [8 empty] | Rocket5 |  |  |  | Closed | R&D Bucket |  | Alpha | Alpha | [6 empty] | Yes | No
key | DevOps |  | Unassigned | Epic: Done | [16 empty] | Unassigned | [8 empty] | Rocket6 |  |  |  | Cancelled | Other |  | Unassigned | Unassigned | [6 empty] | Yes | No
key | DevOps |  | TechComm | Epic: Cancelled | [16 empty] | TechComm | [8 empty] | Rocket1 |  |  |  | Unkown |  |  | RD | TechComm | [6 empty] | Yes | No
key | DevOps |  | QA | Epic: Demo | [16 empty] | QA | [8 empty] | Rocket2 | [6 empty] | QA | QA | [6 empty] | Yes
key | DevOps |  | DevOps | Story: New | [16 empty] | DevOps | [8 empty] | Rocket3 | R1 | [5 empty] | DevOps | DevOps | [6 empty] | Yes
key |  |  | Evolution | Story: Review | [16 empty] | Evolution | [8 empty] | Rocket4 | R2 | [13 empty] | Yes
key | Story |  | No Pasaran | Story: Ready | [8 empty] | 20 | [7 empty] | No Pasaran | [8 empty] | Rocket5 | R3 | [13 empty] | Yes | Yes
key |  |  | Status200 | Story: In Development | [16 empty] | Status200 | [8 empty] | Rocket6 | R4 | [13 empty] | Yes
key | DevOps |  |  | Story: Validation | [8 empty] | 10 | [16 empty] | Rocket1 | R5 | [12 empty] | Development/Internal Support | Yes
key | DevOps |  |  | Story: Demo Checkpoint | [8 empty] | 10 | [16 empty] | Rocket2 | R6 | [12 empty] | Production Support | Yes
key | DevOps |  |  | Story: Done | [8 empty] | 10 | [16 empty] | Rocket3 | R1 | [12 empty] | Planned - Deployment and Release | Yes
key | DevOps |  |  | Story: In Development - On Hold | [8 empty] | 10 | [16 empty] | Rocket4 | R2 | [12 empty] | Planned - Operational Efficiency | Yes
key | DevOps |  |  | Story: Demo Checkpoint - On Hold | [8 empty] | 10 | [16 empty] | Rocket5 | R3 | [12 empty] | Planned - Platform Health | Yes
key | DevOps |  |  | Story: Prototype Done | [8 empty] | 10 | [16 empty] | Rocket6 | R4 | [12 empty] | Planned - Security | Yes
key | DevOps |  |  | Story: Ready for Validation | [8 empty] | 10 | [16 empty] | Rocket1 | R5 | [12 empty] | Time Off / Conferences | Yes
key |  |  |  | Story: Validation - On Hold | [25 empty] | Rocket2 | R6 | [13 empty] | Yes
key |  |  |  | Story: Cancelled | [25 empty] | Rocket3 | R1 | [13 empty] | Yes
key |  |  |  | Tech Debt: New | [25 empty] | Rocket4 | R1 | [13 empty] | Yes
key |  |  |  | Tech Debt: Review | [40 empty] | Yes
key | Tech Debt |  |  | Tech Debt: Ready | [8 empty] | 30 | [31 empty] | Yes
key |  |  |  | Tech Debt: In Development | [40 empty] | Yes
key |  |  |  | Tech Debt: Validation | [40 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | New | [10 empty] | Yes
key | Story |  |  | Tech Debt: Done | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | Ready | [10 empty] | Yes
key | Story |  |  | Tech Debt: In Development - On Hold | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | In Dev | [10 empty] | Yes
key | Story |  |  | Tech Debt: Demo Checkpoint - On Hold | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | Validation | [10 empty] | Yes
key | Story |  |  | Tech Debt: Prototype Done | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | Closed | [10 empty] | Yes
key | Story |  |  | Tech Debt: Ready for Validation | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | Cancelled | [10 empty] | Yes
key |  |  |  | Tech Debt: Validation - On Hold | [8 empty] | 1 | [16 empty] | Rocket2 |  |  |  | Unkown | [10 empty] | Yes
key |  |  |  | Tech Debt: Cancelled | [40 empty] | Yes
key |  |  |  | Bug: New | [40 empty] | Yes
key |  |  |  | Bug: Triage | [40 empty] | Yes
key | Bug |  |  | Bug: Ready | [26 empty] | R1 | Rocket | Highest |  |  |  | Titan | [7 empty] | Yes
key | Bug |  |  | Bug: In Development | [26 empty] | R2 | Rocket | High |  |  |  | Titan | [7 empty] | Yes
key | Bug |  |  | Bug: Validation | [26 empty] | R3 | Rocket | Medium |  |  |  | Titan | [7 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | R4 | Rocket | Low |  |  |  | Titan | [7 empty] | Yes
key | Bug |  |  | Bug: New - On Hold | [26 empty] | R5 | Rocket | Lowest |  |  |  | Titan | [7 empty] | Yes
key | Bug |  |  | Bug: In Development - On Hold | [26 empty] | R6 | Rocket | Low |  |  |  | Titan | [7 empty] | Yes
key |  |  |  | Bug: Validation - On Hold | [40 empty] | Yes
key |  |  |  | Bug: Investigate | [40 empty] | Yes
key | [44 empty] | Yes
key | Bug |  |  | Bug: Closed | [26 empty] | R1 | Rocket | Highest |  |  |  | Titan | [7 empty] | Yes
key | Epic | [8 empty] | Cross Project Move |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Rocket |  |  | DevOps |  |  |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic | [8 empty] | Excel Import |  |  |  |  | 200 | 150 | [5 empty] | 180 | [9 empty] | Rocket |  |  | Excel Import |  |  |  | 30 | 60 | 40 |  |  |  | Yes
key | Epic |  |  | Story: New | [5 empty] | Diagram Editor |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | New | UME v2 |  | Alpha |  | 30 | 60 | 40 |  |  |  | Yes
key | Story |  |  | Story: Ready | [5 empty] | Artifact List |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | Ready |  |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: In Development | [5 empty] | DevOps |  |  | 10 |  | 200 | 150 | [15 empty] | Rocket |  | In Dev |  |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 10 | [18 empty] | Rocket |  | Validation |  |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 10 | [18 empty] | Rocket |  | Closed |  |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 20 | [18 empty] | Rocket |  | New |  |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 20 | [18 empty] | Rocket |  | Ready |  |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 20 | [18 empty] | Rocket |  | In Dev |  |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 20 | [18 empty] | Rocket |  | Validation |  |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 20 | [18 empty] | Rocket |  | Closed |  |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 30 | [18 empty] | Rocket |  | New |  |  | NW | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 30 | [18 empty] | Rocket |  | Ready |  |  | NW | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 30 | [18 empty] | Rocket |  | In Dev |  |  | NW | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 30 | [18 empty] | Rocket |  | Validation |  |  | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [18 empty] | Rocket |  | Closed |  |  | NW | [7 empty] | Yes
key | Story |  |  | Story: New | [8 empty] | 40 | [18 empty] | Rocket |  | New |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Ready | [8 empty] | 40 | [18 empty] | Rocket |  | Ready |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: In Development | [8 empty] | 40 | [18 empty] | Rocket |  | In Dev |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Validation | [8 empty] | 40 | [18 empty] | Rocket |  | Validation |  |  | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 40 | [18 empty] | Rocket |  | Closed |  |  | RD | [7 empty] | Yes
key | [44 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | UME v2 | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | CPM | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | R&D Bucket | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | Other | [9 empty] | Yes
key | Epic | [13 empty] | 200 | [16 empty] | Rocket |  |  | Excel Import | [9 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200 | [15 empty] | R1 | Rocket |  |  | DevOps |  | NW | [7 empty] | Yes
key | Epic |  |  | Story: Done | [8 empty] | 30 |  | 200.125 | [15 empty] | R2 | Rocket |  |  | CI/CD |  | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R3 | Rocket |  |  |  |  | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R4 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R5 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R6 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R1 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R2 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R3 | [5 empty] | Titan | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R4 | [5 empty] | RD | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R5 | [5 empty] | NW | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R6 | [5 empty] | ngStars | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R1 | [5 empty] | Alpha | [7 empty] | Yes
key | Story |  |  | Story: Done | [8 empty] | 30 | [17 empty] | R2 | [5 empty] | Titan | [7 empty] | Yes
key | [44 empty] | Yes
key | DevOps |  |  | DevOps: New | [40 empty] | Yes
key | DevOps |  |  | DevOps: Review | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint | [40 empty] | Yes
key | DevOps |  |  | DevOps: Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: In Development - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Demo Checkpoint - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Prototype Done | [40 empty] | Yes
key | DevOps |  |  | DevOps: Ready for Validation | [40 empty] | Yes
key | DevOps |  |  | DevOps: Validation - On Hold | [40 empty] | Yes
key | DevOps |  |  | DevOps: Cancelled | [40 empty] | Yes | </jt:forEach>

## Notes (hidden)
Changes required for a new Sprint:
1. _ReleaseData sheet:
* Update table G2 - copy the previous sprint data to the current sprint and replace the previous sprint data with historical data.
2. _CumulativeFlowData:
* Update table A1 as above.
3. _ReadinessData sheet:
* Update table B20 as above.
4. _TeamVelocityData sheet:
* Update table K5 - fill in the previous sprint data with historical data.
5. _ActiveSprintData sheet:
* In pivot table D1 - change Last Sprint filter for the current sprint.
* Data > Refresh All.
6. ActiveSprint sheet:
* Update donut slice colors if needed (Refresh All should help to not update colors).